## Reports
SUMMARY OF REPORTS COMPLETED
Report Ownership
No. | SDG Sub-Goal | SDG Indicator | Description | UN | STATSSA | Date Received by Prog Coord | Task Team Leader | Training Provided (Y/N) | Due Date | Date Submitted | Comments
1 | 6.5 | 6.5.2 | Transboundary Cooperation | Yes (UNECE) |  | 2017-05-12 | Terrence Tlala | N | 2017-06-14 | 2017-06-14 | This report was completed prior to Task Teams being established. M Bannister coordinated and consolidated and T Tlala gathered data
2 | 6.3 | 6.3.2 | Water Quality | Yes (UNEP) |  | 2017-06-14 | Lebogang Matlala |  | 2017-07-31 | 2017-08-15 | 6.3.2 and 6.6.1 was submitted as one report as requested by UN. Extension granted to 31 August 2017
3 | 6.6 | 6.6.1 | Water related ecosystems | Yes (UNEP) |  | 2017-06-14 | Lebogang Matlala | Y (Webinar- 20 June 2017) | 2017-07-31 | 2017-08-15 | 6.3.2 and 6.6.1 was submitted as one report as requested by UN. Extension granted to 31 August 2017
4 | 6.1 | 6.1.1 | Water - universal and equitable access |  | Yes | 2017-07-18 | Allestair Wensley | N | 2017-07-21 | 2017-07-21 | 1 page Baseline Report for STATSSA
5 | 6.2 | 6.2.1 | Sanitation - universal and equitable access |  | Yes | 2017-07-18 | Cyprian Mazubane | N | 2017-07-21 | 2017-07-21 | 1 page Baseline Report for STATSSA
6 | 6.3 | 6.3.1 | Wastewater Safely Treated |  | Yes | 2017-07-18 | Zanele Bira-Mupariwa | N | 2017-07-21 | 2017-07-21 | 1 page Baseline Report for STATSSA
7 | 6.4 | 6.4.2 | Water Stress |  | Yes | 2017-07-18 | Thabo Masike | N | 2017-07-21 | 2017-07-21 | 1 page Baseline Report for STATSSA. This report was produced throgh Kobus Kuhn
8 | 6.4 | 6.4.1 | Water Use Efficiency | Yes (UN - Food and Agric |  | 2017-09-09 | Thabo Masike | Y (Webinar- 18 December 2017) | 2017-09-20 | 2017-10-31 | Extension was requested until 31 Oct 2017 and the report submitted on time
9 | 6.5 | 6.5.1 | IWRM | Yes (UNEP) |  | 2017-09-19 | Patrick Mlilo | N | 2017-10-20 | 2017-11-24 | 1 day workshop took place on 23 & 24 November 2017 with report submission completed same day. Extension had been granted from 20 Oct '17 to 24 Nov'17 to allow sufficient time to organise wshop and gain good participation

## Task Teams
Sub Goal | DWS Responsibility
6.1 by 2030, achieve universal and equitable access to safe and affordable drinking water for all | · Allestair Wensley (Team Leader)
· Jan Makhetha (NC)
· Sizwe Madlala (Mp)
· Martha Komape (Lim)
· N Hlengwa (FS)
· Justice Maluleke (NW)
· Stephen Marais
· Noxolo Ncapayi
6.2 by 2030, achieve access to adequate and equitable sanitation and hygiene for all, and end open defecation, paying special attention to the needs of women and girls and those in vulnerable situations | · Cyprian Mazubane (Team Leader)
· Tabita Napakade
· Jan Makhetha (NC)
· Sizwe Madlala (Mp)
· Martha Komape (Lim)
· N Hlengwa (FS)
· Justice Maluleke (NW)
· Solomon Makate
6.3 by 2030, improve water quality by reducing pollution, eliminating dumping and minimizing release of hazardous chemicals and materials, halving the proportion of untreated wastewater, and increasing recycling and safe reuse by x% globally | · Zanele Bila-Mupariwa (Team Leader)
· Lebo Matlala
· Busisiwe Tshabalala
· Yakeen Atwaru
· Peter Viljoen
6.4 by 2030, substantially increase water-use efficiency across all sectors and ensure sustainable withdrawals and supply of freshwater to address water scarcity, and substantially reduce the number of people suffering from water scarcity | · Thabo Masike (Team Leader)
· Khumbu Moyo
· Patrick Mlilo
· Chris Moseki
· Michael Singh
6.5 by 2030 implement integrated water resources management at all levels, including through transboundary cooperation as appropriate | · Patrick Mlilo (Team Leader)
· Beason Mwaka
· Dudu Twayi
· Phumza Dubula
· Jurgo Van Wyk
6.6 by 2020 protect and restore water-related ecosystems, including mountains, forests, wetlands, rivers, aquifers and lakes | · Lebo Matlala (Team Leader)
· Yakeen Atwaru
· Zanele Bila-Mupariwa
· Jacqueline Jay
· Zacharia Maswuma
· Wietsche Roets
· Carey Rajah
6.a by 2030, expand international cooperation and capacity-building support to developing countries in water and sanitation related activities and programmes, including water harvesting, desalination, water efficiency, wastewater treatment, recycling and reuse technologies | · Refiloe Moloi-Owoyomi (Team Leader)
· Patrick Mlilo
· Khumbu Moyo
· Bekubuhle Mbentse
· Celiwe Ntuli
· Dudu Twayi
· Kentse Mathiba
· Miriam Ngoatje
6.b support and strengthen the participation of local communities for improving water and sanitation management | · Iris Mathye (Team Leader)
· Moloko Raletjana
· Bekubuhle Mbentse
· Silo Kheva (MP)
· Justice Maluleke (NW)
· Mogale Matseba (GP)
Sector Support and Coordination | · Iris Mathye (Team Leader)
· Mark Bannister
· Sesi Moselekwa