## Slide 1: PROGRESS ON THE HUMAN RESOURCES TASK TEAM
DATE: 03 DECEMBER 2013

## Slide 2: BACKGROUND
Human Resource Task Team: Objectives
Oversee the change management process in the establishment of CMAs
Ensure that staff transfer and human resources is appropriately managed
Develop a transfer protocol(migration plan)
Finalise a transfer framework agreement
Consult with unions in the change management processes

## Slide 3: Communication and Change Management Strategy
The change strategy and plan intends to support the establishment of the CMAs.
It will address change at the Leadership, Structure, Process and People levels.
The strategy aims to create effective communications and change channels to carry the message to the affected parties.
Identify change agents in the regions and provide training
Create a positive environment and relationship between the staff and management during the process of change.
To ensure participation and sharing of experiences amongst all players for effective change management.

## Slide 4: Preparing for Change Implementation
Task/Activity | Responsibility | Deadline | Status
Communication and change strategy | HR and Comms | Oct 2013 | Endorsed by HR task team
Information Products Q&A brochure | HR, Communications and IO | Nov 2013 | Eastern Cape newsletter and QA well received by stakeholders
Website web page/link with updated information | Communications | Continuous updates | Info available on internet
Employee Engagement Workshops,mtg Migration awareness information letter HR Transaction | DDG/Employee Relations HR Transactions Institutional Oversight All Task Teams | 01/13 - 03/ 2014 | 

## Slide 5: Preparing for Change Implementation
Task/Activity | Responsibility | Deadline | Status
Change Readiness assessment Design change readiness questionnaire | Change Management team |  | 
Create Change Network - Identify Change Agents - Train change agent - Train change champions | Direct Supervisors OD Practitioners Change Team HRD | 20 Feb 2014 | In the next round of RSC will identify CA
Internal communication Q&A leaflet to all officials DWA Speaks magazine, Shotha newsletters, Project Newsletter : every quarter , Intranet, Website, Notice Board | CD: Communications | Continuous | 2nd Ed national newsletter to be approved by COMM, gazette notices, blue screen

## Slide 6: Preparing for Change Implementation
Task/Activity | Responsibility | Deadline | Status
Managing resistance Identify the root cause of not supporting change Address the root cause of resistance Apply the consequences of not supporting change | Change Agent/ Direct Supervisor Direct Supervisor / ER/ Change Agent/ EHWP | ongoing | 
Training and Skills Audit Identifying skills gap Designing and providing training specific programmes Re skilling Employees | HRD | Will be initiated in January 2014 | The Learning Academy is in the process of implementing a skills audit in all the proto CMAS

## Slide 7: Ring fencing of proto CMA staff in Region
Prior to the current restructuring in the DWA, WRM functions were performed by staff in the proto CMAs
Proto-CMAs structures in the 9 regions were not uniformly aligned
In the new regional structure there is no proto CMA
Current thinking :
Ring fence all WRM functions (including finance and HR related to WTE) staff and budget for each WMA.
HR together with RO to identify and ring-fence staff performing the WRM functions in each region

## Slide 8: Transfer Agreement
Draft Transfer agreement developed and aligned to the DPSA policy principles guidelines
  Include GEPF as pension provider
  Adherence to Public Conditions of Services
Consult legal services, Regional offices and unions
Transfer agreement finalized by March 2014

## Slide 9: CMA functional structure
CATCHMENT MANAGEMENT AGENCY
Water Use Catchment Regulation
MINISTER OF WATER AND ENVIRONMENTAL AFFAIRS
Institution & Stakeholder Coordination
Water Information Management
Catchment Strategy, Programmes and Planning
Corporate Services
Section 19 and 20 of f NWA
Water Use Authorisation
Compliance and Monitoring
Enforcement
Institution Establishment
Institution Monitoring
Stakeholder Management
Maintain and monitor data collection
Water Resource Information assessment
Water Resource Data system
Disaster Management
  Floods
  Droughts
  Ecological
Coordinate the development of catchment Management strategy
Water allocation
Planning (WAR)
Planning & Coordination of augmentation and reconciliation
Classification and reserve determination
Develop crisis
interventions
Revenue management
HR services
Finance and supply chain
management
Administration
CMA BOARD

## Slide 10: Recommendations
Implement change and communication strategy in each Region and align to the Regional implementation plan
Migration plan to fit in the CMA generic structure
Ring fence all WRM functions (including finance and HR related to WTE) staff and budget for each WMA.
HR together with RO to identify and ring-fence staff performing the WRM functions in each region
Adopt transfer agreement

## Slide 11: Thank you