## Slide 1
FOURTH NATIONAL STEERING COMMITTEE
PROGRESS REPORT ON ESTABLISHMENT OF CMAS
03 DECEMBER 2013

## Slide 2: PRESENTATION OUTLINE
Progress on the establishment of the RSC
Progress on the establishment of CMA
Regional Support Plan for the Project
Challenges
Recommendations

## Slide 3: Regional Steering Committee
Water Management Area | Progress
Limpopo | Regional Steering Committee (RSC) established 5 RSC meetings held TORs developed and adopted Implementation Plan developed and Presented , Communication Plan developed and Presented Risk Plan not yet developed Draft Business Case available and gazetted for public consultation November 2013 11 Stakeholder Consultation meetings held
Inkomati-Usutu | Regional Steering Committee (RSC) established 4 RSC meetings held Draft TORs developed

## Slide 4
Inkomati-Usutu | Draft Implementation Plan developed, Draft Communication Plan developed Risk Plan not yet developed Business Case was developed and approved by the minister on 31 March 2013. The notice was published on 26 July 2013 4 Stakeholder Consultation meetings held

## Slide 5
Vaal | Regional Steering Committee established 4 RSC meetings held Draft TORs developed Draft Implementation Plan developed, Draft Communication Plan developed Risk Plan not yet developed No Business Case developed yet 40 Stakeholder Consultation took place through the Catchment forums
Orange | Regional Steering Committee established 3 RSC meetings held Draft TORs developed , Draft Implementation Plan developed, Draft Communication Plan developed Risk Plan not yet developed No Business Case Stakeholder Consultation took place through the Catchment forums

## Slide 6
Breede-Gouritz | Regional Steering Committee (RSC) established 5 RSC meeting held Draft TORs developed Draft Implementation Plan developed Draft Communication Plan developed Risk Plan not yet developed Business Case in place and gazzeted for public consultation July 2013 21 Stakeholder Consultation meetings held
Berg Olifants | Regional Steering Committee (RSC) established 5 RSC meeting held Draft TORs developed Draft Implementation Plan developed Draft Communication Plan developed Risk Plan not yet developed Business Case not yet developed 29 Stakeholder Consultation meetings held

## Slide 7: Regional Steering Committee
Olifants -Letaba | Regional Steering Committee (RSC) established 9 RSC meeting held TORs were developed and adopted draft Implementation Plan developed, to be presented in Feb 2014 Communication Plan developed, to be presented in Feb 2014 Risk Plan developed, to be presented in Feb 2014 Draft Business Case developed, was presented to Regional Steering Committee on the 07 and 08 November 2013 5 Stakeholder Consultation meetings held
Mzimvubu-Tsitsikama | Regional Steering Committee (RSC) established 7 RSC meeting held Draft TORs developed Draft Implementation Plan developed Draft Communication Plan developed Risk Plan not yet developed Businesses in the process of development (Situational assessment ) 4 Stakeholder Consultation meetings held

## Slide 8
Phongola-Mzimkhulu | Regional Steering Committee (RSC) established 5 RSC meetings held. TORs developed and adopted Implementation developed , was presented to RSC Communication developed, was presented to RSC Risk Plan not yet developed (but risk factors identified) Draft Business Case available and gazetted for public consultation November 2013 20 Stakeholder Consultation meetings held

## Slide 9: Regional Support Plan for the Project
Water Management Area | Capacity & Skills | Budget
Limpopo | The stakeholders are being empowered and capacitated through the Stakeholders empowerment project | R3 000 000.00 for stakeholder empowerment
Inkomati-Usuthu | Not yet assessed | 41 000 000.00 ICMA and 12 000 000. 00 Usuthu
Olifants-Letaba | There is an ongoing support through Public Participations, workshops and meetings. The capacity building projects were undertaken. The stakeholder’s empowerment project will commence soon to empower the stakeholders in Water Resource Management. | R980 000.00 (estimation) for stakeholder empowerment

## Slide 10
Water Management Area | Capacity & Skills | Budget
Vaal | Limited capacity | Nothing set aside for establishment of the CMA
Orange | Limited capacity | No budget set aside for establishment of the CMA
Phongola-Mzimkhulu | The Region supports head office in the roll-out of the CMA process. A team of 16 staff members work across the Province and assist with stakeholder liaison, dissemination of information and the facilitation of comments on the various documentations distributed with regards to the establishment of the CMA. | R151 400.00 (estimation) for stakeholder empowerment

## Slide 11
Water Management Area | Capacity & Skills | Budget
Breede-Gouritz | Limited capacity | No budget set aside for establishment of the CMA
Berg-Olifants | Not yet assessed | No budget set aside for establishment of the CMA
Mzimvumbu-Tsitsikama | There is enough staff in the unit to support the establishment of the CMA. The skills are minimal PSP was appointed to assist with the development of the business case. | R791 000-00 for the development of the Business Case

## Slide 12: Challenges
Lack of policies and guidelines regarding the following areas
  Guideline on CMA remuneration policy
  Guideline on rules of engagement between CMA and RO.
  Guidelines on the establishment and post establishment of CMAs. This will assist Regions in creating a sustainable institution.
  Guidelines on the procedures in aligning systems.
  A clear distinction of roles and responsibilities between the R/O and the CMA.
  Guidelines on the CMA remuneration packages.
  Policies on the transfer of staff, budget and other resources from DWA and the Regional office.

## Slide 13: Challenges
Lack of policies and guidelines regarding the following areas
  A clear list of delegations and assignment to the CMA.
  Guidelines on the “rules of engagement” between the CMA and the R/O
  Policy on the regulation of CMAs by the R/O.
unavailability of reimbursement
Where there are no resources & capacity allocated it is bound to create delays and compromise the quality of work.

## Slide 14: Recommendations
The establishment must be project driven , a decision must be made on how the process will be taken forward.
Implementation of reimbursement policy.
The establishment of the CMA is a sensitive issue i.t.o politics. There is a critical need for higher-level engagements with strategic stakeholders like SALGA
Direction needs to be given to staff regarding staff transfer issue. Currently there are a lot of uncertainty and fear from staff which needs to be urgently addressed.
Clear direction on this issue must be provided through the establishment of appropriate policies and guidelines.
Linking Provincial Strategic Objectives with the CMA (Provincial Growth & Development Strategy/ CMS).

## Slide 15
Thank you