## Slide 1
ESTABLISHMENT OF THE PHONGOLA TO MZIMKHULU CMA
PRESENTED BY:
MR J.G REDDY

## Slide 2
PHASED ESTABLISHMENT PLAN FOR 9 CMAs
Phase 1 | Phase 2 | Phase 3
Inkomati – Usuthu | Berg-Olifants | Orange
Breede Gouritz | Vaal | Mzimvubu-Keiskamma
Pongola-Umzimkulu | Olifants | 
 | Limpopo | 

## Slide 3: 3 WMAs in KZN

## Slide 4
Planning meetings were held between DWA Head Office and the Regional Office in July 2012 to discuss the CMA establishment process for KZN.
Approximately 3 RSC meetings has been held to date:
KZN REGIONAL STEERING COMMITTEE
Date | Key milestones achieved
3 August 2012 | Draft T.O.R was further discussed and adopted. Decision taken to keep the RSC to internal DWA members and formalised structures representing external stakeholders were to be set up. Representatives from the formalised structures will eventually become members of the RSC.

## Slide 5
Cont……
Date | Key milestones achieved
20 September 2012 | Draft stakeholder engagement plan was discussed and commented on. The requirements of the BP was presented.
9 November 2012 | Feedback on the stakeholder engagement sessions was provided. Draft BC for the Phongola –Mzimkhulu CMA was presented. Stakeholder Engagement Plan was approved. Draft implementation plan was presented and discussed. Decision taken to establish three Reference Groups as per each of the WMA.
Next RSC meeting is scheduled in March 2013.

## Slide 6
3 x Stakeholder engagement meetings took place as follows:
- 9 October 2012, Ladysmith
- 10 October 2012, PMB
- 11 October 2012, Richard’s Bay
The purpose of these meetings were to engage stakeholders on the following:
  the outcome of the IRR project i.t.o 9 CMAs, provide an understanding of the legislative framework and processes involved in establishing CMAs, the rational and requirements for developing the Business Case, to obtain input on the draft CMA Engagement Plan and the nomination of the Reference Groups.
All three meetings were well attended by a range of stakeholders.
Concerns at these meetings centered around political interference, a change of Minister resulting in a change of the Minister’s priorities and the viability of the CMA.
However, despite these concerns the overall message from the stakeholders was “lets just get going with this long awaited process”.
STAKEHOLDER ENGAGEMENT MEETINGS

## Slide 7
Further stakeholder engagements entailed the following:
  Presentations and discussions on the CMA process in each of the 21 CMFs in KZN.
  Placement of notices on the CMA process in several newspapers in both isiZulu and English.
  Development and circulation of the CMA newsletter to stakeholders.
  Engagement with the Inkomati CMA and the Mphumalanga R/O on the transfer of the Usutu Catchment .
  A 2- day Lesson Sharing Workshop was held with BOCA and the Western Cape Regional Office. Purpose was to engage on their experiences and knowledge on the establishment and post establishment phases of the CMA.
Cont…..

## Slide 8
Planned Stakeholder Engagement Activities for February/ March 2013:
  An Internal Regional Engagement Session is scheduled for the 20 of February 2013. The purpose is to sensitize and educate staff on the concept of the CMA as well as to address the concerns and fears in relation to staff matters.
  An Inkomati RSC meeting is scheduled for the 12th of February 2013. On the 13th of February, the team from Inkomati will be introduced to the Mkhondo CMF.
  3 x Reference Group meetings are scheduled for the 4th, 5th and 6th of March 2013.
  The purpose of these meetings is mainly to discuss the draft Business Case and highlight the way forward as per the CMA Implementation plan.
  The 4th RSC meeting will take place at the end of March 2013.
Cont…..

## Slide 9
The BC is approximately 90% complete as per the requirements by Treasury.
However, it still requires input from various stakeholders and the alignment of the BC as per the needs and dynamics of the Phongola to Mzimkhulu WMA.
Further discussion on the financial model and organisational structure of the CMA is required.
Copies of the draft BC are being circulated to both internal and external stakeholders for review and comment.
PROGRESS ON THE DEVELPMENT OF THE BUSINESS CASE: PHONGOLA TO MZIMKHULU

## Slide 10
Appointment of a Regional PSP to assist with some of the following:
  Support to the Advisory Committee.
  Extensive Capacitation and Empowerment of the Governing Board.
  Assistance in setting up the actual institution i.t.o. venue selection etc.
  Support to the CEO in terms of appointment of staff, alignment of systems, policies and procedures to DWA.
  Assisting with the drafting of policies
SUPPORT PLAN REQUIRED FOR THE PROJECT

## Slide 11
There is clearly a lack of policies and guidelines regarding the following:
  Guidelines on the establishment and post establishment of CMAs. This will assist the Regions in creating a sustainable institution.
  Guidelines on the procedures in aligning systems, strategic objectives of department and reporting and regulation.
  A clear distinction of roles and responsibilities between the R/O and BOCMA.
  Guidelines on the remuneration packages for the CMA organogram.
  Policies on the transfer of staff, budget and other resources from DWA and the Regional office.
  A clear list of delegation of functions and budget to the CMA.
CHALLENGES & RECOMMENDATIONS