## Slide 1
THIRD NATIONAL STEERING COMMITTEE
PROGRESS AND LESSON LEARNED ON THE ESTABLISHMENT OF CMAS BY
THE REGIONS
31 MAY 2013

## Slide 2: PRESENTATION OUTLINE
Progress on the establishment of the RSC
Progress on the establishment of CMA
Regional Support Plan for the Project
Challenges
Lessons learnt and Recommendations

## Slide 3: Regional Steering Committee
Water Management Area | Progress
Limpopo | Regional Steering Committee established 4 RSC meetings held TORs finalised Implementation Plan finalised , Draft Communication Plan developed Risk Plan not yet developed Draft Business Case developed and almost completed 9 Stakeholder Consultation meeting held
Inkomati-Usutu | Regional Steering Committee established 6 RSC meeting held TORs finalised Draft Implementation Plan is in place and circulated for input, Draft Communication Plan is in place and circulated for input Risk Plan not yet developed Business Case finalised, approved and submitted to NT for listing Proposal for establishment of the CMA has been signed by the minister for public comments 2 Stakeholder Consultation meeting held
Olifants/ Letaba | Regional Steering Committee established 4 RSC meetings held. TORs not yet adopted, draft Implementation Plan developed Communication Plan not yet developed Risk Plan not yet developed Draft Business Case available 5 Stakeholder consultations meeting held
Notes: Gazette for the establishment of Inkomati-Usuthu CMA will be published soon for comments, it is an opportunity for regions to engage with stakeholders to get further input, concerns around the establishment of CMAs

## Slide 4
Vaal | Regional Steering Committee established 3 RSC meetings held TORs finalised, Implementation Plan finalised, Draft Communication Plan is in place Risk Plan not yet developed No Business Case developed yet Stakeholder Consultation took place through the Catchment forums
Orange | Regional Steering Committee established 3 RSC meetings held TORs are in place , Implementation Plan finalised, draft Communication Plan developed Risk Plan not yet developed No Business Case Stakeholder Consultation has not yet commenced
Phongola-Mzimkhulu | Regional Steering Committee established 4 RSC meetings held. TORs finalised Implementation Plan finalised Communication Plan finalised Risk Plan not yet developed (but risk factors identified) Draft Business Case available almost completed 9 Stakeholder consultations meeting held

## Slide 5
Breede-Gouritz | Regional Steering Committee established 2 RSC meeting held TORs finalised Draft Implementation Plan is in place and circulated for input, Draft Communication Plan is in place and circulated for input Risk Plan not yet developed Business Case finalised and submitted to NT for listing Proposal for establishment of the CMA has been signed by the minister and submitted to NT for listing Stakeholder Consultation has not yet commenced
Berg Olifants | Regional Steering Committee established 2 RSC meeting held TORs not yet adopted, Draft Implementation Plan developed Communication Plan not yet developed Risk Plan not yet developed Business Case not yet developed Stakeholder Consultation has not yet commenced
Mzimvubu-Tsitsikama | Regional Steering Committee established 4 RSC meeting held TORs finalised, Implementation Plan finalised, Draft Communication Plan is in place Risk Plan not yet developed No Business Case developed yet( in progress of being developed) Stakeholder Consultation has not yet commenced
Notes: Gazette for the establishment of Breede-Gouritz CMA will be published soon for comments, it is an opportunity for regions to engage with stakeholders to get further input, concerns around the establishment of CMAs

## Slide 6: Regional Support Plan for the Project
Water Management Area | Capacity & Skills | Budget
Limpopo |  | R4000 000 for stakeholder empowerment
Inkomati-Usuthu |  | R100 000
Olifants/Letaba |  | R980 000.00 (estimation) for stakeholder empowerment

## Slide 7
Vaal | Limited Capacity | Nothing set aside for establishment of the CMA
Orange | Limited capacity | Nothing set aside for establishment of the CMA
Phongola-Mzimkhulu |  | R151 400.00 (estimation) for stakeholder empowerment

## Slide 8
Breede-Gouritz | Limited Capacity | Nothing set aside for establishment of the CMA
Berg |  | Nothing set aside for establishment of the CMA
Mzimvumbu-Tsitsikama | Limited Capacity However the PSP will assist in capacitating officials as per the TORs | Nothing set aside for establishment of the CMA however there is allocation of 791 000 for the development of the Business Case

## Slide 9: Challenges
Lack of policies and guidelines regarding the following areas:
  Guideline on CMA remuneration policy
  Guideline on rules of engagement between CMA and RO.
  Guidelines on the establishment and post establishment of CMAs. This will assist Regions in creating a sustainable institution.
  Guidelines on the procedures in aligning systems.
  A clear distinction of roles and responsibilities between the R/O and the CMA.
  Guidelines on the CMA remuneration packages.
  Policies on the transfer of staff, budget and other resources from DWA and the Regional office.
  A clear list of delegations and assignment to the CMA.
  Guidelines on the “rules of engagement” between the CMA and the R/O
  Policy on the regulation of CMAs by the R/O
Some Catchment Forums are reluctant to attend due to unavailability of reimbursement
Where there are no resources & capacity allocated it is bound to create delays and compromise the quality of work.
Notes: The challenges are from the regions, where explanation is not clear, please assist to detail your input

## Slide 10: Lessons learnt & Recommendations
The establishment must be dealt with like a project, a decision must be made on how the process will be taken forward.
DWA should implement a reimbursement policy.
The establishment of the CMA is a sensitive issue i.t.o politics. There is a critical need for higher-level engagements with strategic stakeholders like SALGA
Based on the 2 functional CMAs, the transfer of staff was not possible (specifically for the ICMA) due to the constraints of existing policies and legislation. Where establishment processes are underway, direction needs to be given to staff regarding this issue. Currently there are a lot of uncertainty and fear from staff which needs to be urgently addressed.
Clear direction on this issue must be provided through the establishment of appropriate policies and guidelines.
Linking Provincial strategic objectives with the CMA (Provincial Growth & Development Strategy/ CMS).
Notes: The comments are also from the regions, where explanation is not clear, please assist to detail your input

## Slide 11
Thank you