## Slide 1: NATIONAL STEERING COMMITTEE MONITORING AND INFORMATION SYSTEMS FOR CMAs TASK TEAM 31 May 2013

## Slide 2: Contents
Roadmap
Progress to date
Way Forward

## Slide 3: Road Map
Task Team Established
(4/4/13)
TOR
Info Gathering
High level functions
Business case input requirements
Critical success factors/ enablers
Systems relating to info
Info aligned to functions
Processes, roles
Dependencies
Alignment to all task teams
Input to business case
Test
Refine and finalise
Support implementation

## Slide 4: Road Map
Task Team Established
(4/4/13)
TOR
Info Gathering
High level functions
Business case input requirements
Critical success factors/ enablers
Systems relating to info
Info aligned to functions
Processes, roles
Dependencies
Alignment to all task teams
Input to business case
Test
Refine and finalise
Support implementation

## Slide 5: TOR
Composition of the task team
- WRIM (including SLIM, HS, NIWIS, RQS), Revenue Management (SAP), CMA, Regional Co-ordination, IO, Reg: Co-ord / Regions, OCIO
- Expert input from extended task team members

## Slide 6: TOR
TT Functions
ID Info & Monitoring Systems to be used/ transferred to CMA
Document a functional model which will guide DWA / CMA wrt business processes, IT infrastructure and IS;
Review policies
Provide guidance on monitoring and information systems
Provide a plan on data management

## Slide 7: Road Map
Task Team Established
(4/4/13)
TOR
Info Gathering
High level functions
Business case input requirements
Critical success factors/ enablers
Systems relating to info
Info aligned to functions
Processes, roles
Dependencies
Alignment to all task teams
Input to business case
Test
Refine and finalise
Support implementation

## Slide 8: Information Gathering
Task team meetings and discussions
Documentation
  OCIO – business processes, lessons learned
  CMAs – business processes, lessons learned
  Existing documentation
  NIWIS
Implementation Matrix

## Slide 9: Road Map
Task Team Established
(4/4/13)
TOR
Info Gathering
High level functions
Business case input requirements
Critical success factors/ enablers
Systems relating to info
Info aligned to functions
Processes, roles
Dependencies
Alignment to all task teams
Input to business case
Test
Refine and finalise
Support implementation

## Slide 10: Implementation Matrix Phase CMA Functions and Activities DWA Lead Unit HO Role & Enablers Standards & Guidelines CMA Role CMA Processes Information Needed Systems in DWA CMA Access Required Comments

## Slide 11: Progress to date
Task Team Established
(4/4/13)
TOR
Info Gathering
High level functions
Business case input requirements
Critical success factors/ enablers
Systems relating to info
Info aligned to functions
Processes, roles
Dependencies
Alignment to all task teams
Input to business case
Test
Refine and finalise
Support implementation

## Slide 12: Way Forward
Task Team Established
(4/4/13)
TOR
Info Gathering
High level functions
Business case input requirements
Critical success factors/ enablers
Systems relating to info
Info aligned to functions
Processes, roles
Dependencies
Alignment to all task teams
Input to business case
Test
Refine and finalise
Support implementation

## Slide 13: Future items for consideration
Starter pack
Hard copy filing system
Implementation Matrix

## Slide 14: Thank you