## Slide 1: PROGRESS IN THE ESTABLISHMENT OF CMAS 3rd National Steering Committee for the establishment of CMAS in SA 31 MAY 2013

## Slide 2
CORE BUSINESS
TOP TEN RISKS
PROGRESS AND KEY TIMELINES | 
19 March 2012 | Minister approved the establishment of nine CMAs in nine WMAs
21 May 2012 | Gazetting of WMAs for public consultation approved.
June 2012 | National Steering Committee established to oversee implementation (DWA, National Treasury, SALGA,CMAs, Civil Society.)
20 July 2012 | Gazette published (No 35517 ) on proposed WMA.
31 March 2013 | Business Cases and Proposals for Inkomati - Usuthu and Breede Gouritz CMAs approved by Minister for gazetting establishment notices for comment.

## Slide 3
CORE BUSINESS
TOP TEN RISKS
PROGRESS AND KEY TIMELINES | 
June 2013 | Business Cases for Limpopo and Pongola Umzimkhulu, developed and prepared for Minister’s signature for gazetting notices for comment for 60 days.
August 2013 | Gazette notices for the establishment of Inkomati Usuthu and Breede Overberg CMAS published.
September 2013 | Finalise the new process on appointing of the Board. Board appointments for Inkomati-Usuthu Limpopo, Umzimkhulu, and Breede-Gouritz CMAS will commence
March 2014 | Business plans submitted to Minister from Inkomati-Usuthu and Breede-Gouritz CMAS

## Slide 4: Water Management Areas
Limpopo
Olifants
Vaal
Orange
Berg-Olifants
Pongola-Mzimkulu
Mzimvubu-Tsitsikamma
Breede-Gouritz
Inkomati-
Usuthu

## Slide 5
Establishment Phase
Operation Phase
CMA IMPLEMENTATION PLAN
Preparatory Phase
Aug12-July 13
Sustain & Improve
Aug 14-July 15 and beyond
Gazetting of WMAs
Appointment of Chief Executive
Time Frames
Project Phases
Cross Cutting Activities
Approach
PHASE 2 : Berg-Olifants-Doorn , Vaal , Olifants and Limpopo
1 Month
2 Months
1 Month
PHASE 1 : Breede-Gouritz, Inkomati-Usuthu and Pongola Mzimkhulu
PHASE 3 : Orange, Mzimvubu-Keiskamma
Implementation of Initial Functions
Delegation of functions
Office Accommodation
8 Months
HIGH LEVEL PROJECT PLAN FRAMEWORK
Finalising Business Cases
Approval of Business Cases by NT and listing under PFMA
Gazetting of CMAs
Appointment of Governing Board
Setting up of National Steering Committee
Setting up of Regional Steering Committees
Budget secured MTEF
Human Resources
Systems
Aug12-July 13
Aug13-July 14
Aug14-July 15 and beyond
Aug13-July 14
Appointment of dedicated team

## Slide 6
Business Process Review Committee
PROJECT GOVERNANCE ARRANGEMENTS
Minister
DG
DDG Policy & Regulation
CD Institutional Oversight
Project Manager & Selected Officials
WSLG
National STEERING COMMITTEE
Regional
Steering Committees
Olifants
Inkomati-Usuthu
Breede-Gouritz
Project Sponsor
Project Champion
Project Leader
Project Office
Review pricing & funding strategy
Economic Regulator
NWRS
Legislative Review
IRR
Flagship Projects
Need for PMO
Limpopo
Pongola-Mzimkhulu
Berg- Olifants
Inkomati-Usuthu
Olifants
Mzimvubu to Keiskamma
Breede-Gouritz
Vaal
Orange
PROJECT GOVERNANCE ARRANGEMENTS

## Slide 7
NWRI
WB
2+1
WB
3
CMA 9
CMA 2
CMA 1
Water board 3
TCTA
Minister
DWA
Institutional oversight (national & regional)
Parliament
Public institutions report to the public and Parliament through Annual Reports and Annual Financial Statements and to the Department with quarterly performance
reports
WRC
Minister appoints boards; approves shareholder compact
Portfolio Committee reviews reports and plans (hearings, visits)
Oversee institutional establishment;
Oversee governance (manage board appointment processes, training etc.);
Oversee shareholder compact;
Oversee business plans, quarterly performance reports and financial statements etc.
279 WUAs &Irrigation Boards
GOVERNANCE
7
Notes: Elaborate on this, add government water schemes

## Slide 8
Support Area | Document | Purpose | Level of effort
Process | Start-up process guide | Overarching guide that describes the start-up processes, the inter-linkages, responsibilities and time frames | M
Governing Board | Board Training Manual | Framework for the Board training including materials | M
 | Board Charter | Outlines Board processes and conduct to ensure good governance | L
 | Shareholder Compact | Effectively provides a service level agreement between the Board and the Minister | L
 | Committee Structure | Outlines the governance committees that are needed, how often they need to meet and how these should be made functional | L
 | Business Plan Template | Guides the structure of the business plan aligned to the governmental planning processes. Some degree of process/protocol are needed (so not just a template) | L
 | Board Performance System | To ensure good governance Board members need to perform, and they need to understand what this entails | M
DEVELOPMENT OF STARTERPACK

## Slide 9
Organisational | Human Resource Policies | Range of policies that guide recruitment, job evaluation and performance management. | M
 | Procurement system | Clear guidance on procurement, aligned to governmental approaches, is necessary | L
 | CMA Structures and salary scales | Provides a guide of how CMAs, of different natures, could be structured and includes provisional salary scales | M
 | *Remuneration policy for CEOs | DWA needs to provide stronger oversight on this and will develop regulations, therefore, this guide provides the first step to ensure salaries are aligned to governmental scales | L
 | *Draft CEO Contract | Linked to the above, there is a need to set out the roles and responsibilities of the CEO. NT would actually prefer to see this contract. | L
 | Asset and equipment Management | Provides a framework for the management of transferred and new assets and equipment. This is needed early in the establishment process. | M

## Slide 10
Financial | Systems requirements and transfer | Provides a framework for the development of systems needed to generate revenue and establish financial controls | M
 | Systems protocols | Guides the exchange of information and data between CMA and DWA | M
Institutional Performance | Quarterly reporting | Provides a reporting framework. Must include financials | L
 | Annual reporting frameworks | Outlines the annual reporting framework. | L
Catchment Management Strategy | Guidelines for the development of a CMS | Outlines the contents of the CMS and needs to provide the actual processes required (current guide does not do this and is dated) | H

## Slide 11
PROGRESS OF THE ESTABLISHMENT CATCHMENT MANAGEMENT AGENCIES
Fast track development of business cases
  Require to develop Vaal and Orange business cases asap
  Eastern Cape RO initiated Mzimvubu Tsitsikamma
  Western Cape RO will finalise Berg-Olifants business case
Meeting with National Treasury to list Inkomati Usuthu and Breede Gouritz CMAs
Amendment of the process to appoint governing board in the National Water Act
Finalise the Starterpack
Established 4 task teams Monitoring and information, delegation of functions, HR and Financial arrangements.

## Slide 12
Water Management Areas | Proposed WMA CMAs | Governing Board Appointed | No of Proto CMA staff | No. of Vacant Proto-CMA Posts | Estimated Full Staff Compliment for new CMA
1. Limpopo | Limpopo | 2013/14 | 62 | 15 | 
2. Crocodile West Marico |  |  | 91 | 53 | 
3. Levhuvu-Letaba | Letaba- Olifants | 2015/16 | 43 | 07 | 
4. Olifants |  |  | 65 | 36 | 
5. Inkomati CMA | Inkomati -Usuthu | 2012/13 | 4 | 0 | 
6. Usuthu |  |  | 3 | 0 | 
6. Mhlatuze | Thukela, Mvoti to Umzimkulu | 2014/15 | 28 | 14 | 
7. Thukela |  |  | 40 | 12 | 
11 . Mvoti to Umzimkulu |  |  | 38 | 18 | 
[G1]

## Slide 13
Water Management Areas | Proposed CMAs | Governing Board Appointed | No of Proto CMA staff | No. of Vacant Proto-CMA Posts | Estimated Full Staff Compliment for new CMA
8. Upper Vaal | Vaal | 2014/15 | 96 | 30 | 
9. Middle Vaal |  |  | 9 currently + 16 additional post created | 22 | 
10. Lower Vaal |  |  | (Region is not sure)16 | 19 | 
12. Mzimvubu to Keiskamma | Mzimvubu to Keiskamma & Fish to Tsitsikamma | 2015/16 | 23 (for both WMAs 12 and 15) |  | 
15. Fish to Tsitsikamma |  |  | 23 (for both WMAs 12 and 15) |  | 
13. Upper Orange | Orange | 2015/16 | 31 | 22 | 
14. Lower Orange |  |  | 18 | 17 | 
16. Gouritz | Breede &Gouritz | 2012/13 | 13 | 10 | 
18. Breede- Overberg CMA |  |  | 0 | 0 | 
17. Olifants-Doorn | Olifants/Doorn & Berg | 2015/16 | 15 | 9 | 
19. Berg |  |  | 12 | 15 | 
[G1]

## Slide 14: NEXT STEPS
2 Business cases will be on route to Minister in June
3 Business cases to be initiated within next two months
Task teams established and developing implementation plan
Regional Coordination to identify which Regions to represent task teams
Regional Steering Committee meetings to inform stakeholders of current plans/processes
Regional communication strategy to include Directorate Communication
Update Risk plan

## Slide 15: COMMENTS/QUESTIONS THANK YOU