ANNEXURE 1

WESTERN CAPE FEASIBILITY STUDIES

Surface water options

Project Progress as at end August 2009

Duration: 		43 months

Start Date:		Sep 2008

Completion:		Mar 2012

Phase 1 – Inception: Preliminary assessment of 6 options & prioritization of options for further study:

3 from the Breede River:

Michell’s Pass Diversion

Molenaars River Diversion

Upper Wit River Diversion

2 from the Berg River:

1st Phase Augmentation of Voëlvlei Dam

Further Phases Voëlvlei Dam Augmentation

1 from the Palmiet River

Further Development of Palmiet Transfers

Phase 1 – Inception: Reserve determinations

Undertook specialist field visit (July 2009)

Undertook eco-classification and flow measurement

Held technical Reserve Workshop (July 2009)

Generated naturalised hydrology

Currently determining desktop EWRs with   adjustment for field observations

Finalizing specialist reports

Breede River

Rivers

83 nodes have been delineated

Naturalised flow hydrology has been determined

Flow sequences have been extrapolated

Low flow sequences have been extrapolated

Draft report due 31 Aug 2009.

Estuary

Existing information to be used

Palmiet Catchment

Rivers

All nodes delineated

Naturalized flow hydrology in progress

Draft report (rivers) due in Oct 2009

Estuary

Scenarios development in progress

EWR Specialist workshop (14-18 Sep 2009)

Draft Report due at end Oct 2009

Berg Catchment

Rivers

Delineation of nodes completed

Naturalised flow hydrology in progress

Draft Report due in Oct 2009

Estuary

Scenarios have been provided to Estuary Team

Specialist workshop scheduled for 19-23 Oct 2009

Draft Report due Dec 2009

Upper Wit River Diversion - Overview

Scheme conceptual aspects assessed:

Diversion weir

Transfer tunnel

Receiving channel

Receiving dam

Potential water users: Urban & Irrigation exchange

Upper Wit River Diversion: Progress

Assessed existing “Gawie-se-Water” diversion

Patched gaps in observed DWA record

Disaggregated EWRs to Daily Flows

Produced available total flows

Produced divertible volumes curves

Determined capacity – surface area relationship

Molenaars River Diversion - Overview

Scheme conceptual aspects assessed:

Weir with possible boulder trap, fish ways etc

Pump station location

New pipeline to tunnel entrance

Information required on existing pipeline through tunnel

New pipeline to gravitate water to Berg River Dam / Wemmershoek Dam

Molenaars River Diversion: Progress

Patched gaps in DWA flow record

Disaggregated EWRs to daily flows

Produced available total flows

Produced divertible volumes curves

Determined capacity – surface area relationship

Michell’s Pass Diversion - Overview

Scheme conceptual aspects assessed:

Diversion weir

Siphon and canal (or pipeline) to Klein Berg River

Transfer of water to existing Voëlvlei Diversion

Existing canal to Voëlvlei Dam

Possible raising of Voëlvlei Dam

Michell’s Pass Diversion: Progress

Patched flow records for H1H006 & H1H022

Generated daily present day flow time series

Disaggregated EWRs to daily

Produced available total flows

Produced divertible volumes curves

Public Process:

Public Meetings held on: 5 March 2009 (Grabouw); 7 March 2009 (Worcester)

Stakeholder Committee Meeting held on: 31 March 2009 (Elsenburg)

Upcoming public engagements:  Stakeholder Committee Meeting: Wed 27th January 2010

Options Prioritization Workshop: Wed 10 Feb 2010

Way Forward: Inception Phase

Determine yields of Breede Diversion Schemes

Assess downstream impacts (Breede) on Brandvlei Dam & Irrigators

Commence work on Berg Options (Voëlvlei Dam)

Commence work on Palmiet Options

Finalize Inception Report (Sep 2009)

Ongoing Public Participation

Completion of Reserve Tasks

Facilitate Prioritization Workshop (Feb 2010)

Compile Prelim Assessment Report (Mar 2010)