ANNEXURE 3

Feedback from the All Town Reconciliation Strategy Study

On the next page the present programme of the All Town study for the completion of the first drafts for the Local Municipalities in the Western Cape Province can be seen.  Those strategies that have been identified as urgent are completed.  The next round of strategies, those for the Overberg and Cape Winelands which will be important for the Breede River-Overberg CMA’s Catchment Management Strategy, will be ready by the end of September 2010.  All the draft strategies for the Western Cape Province will be finalised by the end of November 2010.  Unfortunately most of the strategies that overlaps with the work of the Strategy Steering Committee of the Western Cape Reconciliation Strategy will only be completed by November 2010.

On completion of the draft strategies of all the Local Municipalities within a District Municipality (DM), a draft summary report for each DM is also compiled.  The only one available for the Western Cape Province at the moment is the one for Eden DM.  According to the programme the DM summaries for Overberg will be available by the end September, Winelands by end October and West Coast and Central Karoo by end November 2010.

A very short Provincial strategy that summarises the most important findings is scheduled for early next year.

G van Zyl

August 2010