## Slide 1: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Wednesday, 7 April 2021

## Slide 2: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Item 2: Attendance and Apologies

## Slide 3: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Item 3: Acceptance of Agenda

## Slide 4: Agenda

## Slide 5: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Item 4: Purpose of Meeting

## Slide 6: Purpose
FINAL STRA SC MEETING OF THIS PHASE OF STUDY
      Continuation Phase being Initiated
PRESENT DRAFT STRATEGY
PRESENT AND GAIN APPROVAL FOR INTERVENTION ACTION PLAN AND RESPONSIBILITIES

## Slide 7: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Item 5: Minutes and Matters Arising

## Slide 8: ACTION LIST

## Slide 9: ACTION LIST

## Slide 10: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Item 6: Draft Updated Recon Strategy

## Slide 11: OVERVIEW: TOC
Exec Summary
      For document, “glossy” extended executive summary to be completed as separate deliverable
INTRODUCTION & CONTEXT
SUMMARY CHAPTERS ON INDIVIDUAL TASKS DETAILED IN STAND ALONE TECHNICAL REPORTS
        Demographics & water requirements
        WCWDM
        Water Resources Availability

## Slide 12: OVERVIEW: TOC
CURRENT WATER BALANCES
AVAILABLE INTERVENTION OPTIONS
WATER BALANCES INCLUDING OPTIONS
PROPOSED ACTION PLAN
WAY FORWARD

## Slide 13: STUDY AREA

## Slide 14: Water REQUIREMENTS

## Slide 15: Water REQUIREMENTS

## Slide 16: POSSIBLE INTERVENTION OPTIONS
REDUCE WATER USE
        WCWDM
        Remove alien vegetation
        Water Reuse

## Slide 17: WCWDM
Indicator | Current Value | Realistic Target value 10% Reduction | Optimistic Target Value 20% Reduction
System Input volume (million m3/a) | 39,15 | 34.89 | 32.23
System Input volume (Mℓ / day) | 107,19 | 95.54 | 88.24
Billed Authorised Consumption (million m3/a) | 30,00 | 24.32 | 23.89
Unbilled Authorised Consumption (million m3/a) | 1,95 | 4.52 | 4.47
Water Losses (million m3/a) | 7,20 | 6.06 | 3.87
Non-revenue Water (million m3/a) | 9,15 | 10.57 | 8.34
% Non-revenue water | 43% | 30% | 26%
% Water Losses | 24% | 17% | 12%
Input Volume (litres / capita / day) | 277 | 246 | 228
Input Volume (m3 / household / month) | 35 | 31 | 29
Authorised Consumption (litres / capita / day) | 226 | 204 | 200
Authorised Consumption (m3 / household / month) | 29 | 26 | 26
CoMLM: +- 6 million m3 by 2025
Kcdm: +- 0.6 million m3 by 2025

## Slide 18: Remove alien vegetation

## Slide 19: WATER REUSE
CoMLM DRIVEN INTERVENTION
ADVANTAGES
TARGET 30 ML/D (11 MILLION M3)
ONGOING INVESTIGATIONS OF PPP
Utilisation of a potential water source previously “lost” by being discharged into the sea at Alkantstrand;
Reduced demand on natural resources by industrial users;
Augmentation of the Municipality’s potable water resources through a source capable of producing a constant reliable output, influenced to a limited extent by drought cycles, as water demand is expected to slightly decrease when water restrictions are implemented.

## Slide 20: POSSIBLE INTERVENTION OPTIONS
INCREASE WATER SUPPLY
        Efficient system operation
        Implement Operating Rules
        Transfers from neighbouring catchments
        New Dam Construction
        Existing Dam Raising

## Slide 21: EFFICIENT SYSTEM OPERATION
REAL TIME OPERATIONS TO DETERMINE RELEASES FROM GOEDERTROUW DAM
MAXIMUM USE FROM LAKE MZINGAZI

## Slide 22: TRANSFERS FROM THUKELA
MAINTAIN EXISTING TRANSFER AND COMPLETE UPGRADE (1.2 M3/S TO 2.4 M3/S)

## Slide 23: New dam construction
Nseleni river
55 million m3 storage
12 million m3/a yield

## Slide 24: Existing dam raising
Goedertrouw dam
2.8m
12 million m3/a additional yield

## Slide 25: PREVIOUS OPTIONS CONSIDERED
DESALINATION OF SEAWATER
LOWER THUKELA PIPELINE TRANSFER
UMFOLOZI OFF CHANNEL STORAGE DAM

## Slide 26: WATER BALANCES

## Slide 27: MHLATHUZE SYSTEM: CURRENT WATER BALANCE

## Slide 28
Water requirement projection scenarios

## Slide 29: Reconciliation of scenario A
allocation

## Slide 30: Reconciliation of scenario B
allocation
Umfolozi / Desalination

## Slide 31: Reconciliation of scenario D
allocation

## Slide 34: PROPOSED ACTION PLAN
INSTITUTIONAL RESPONSIBILITY
        DWS
        Municipalities
        Mhlathuze Water
TIME FRAMES

## Slide 35
Intervention | Primary Responsibility | Comments | Target Date (priority)
WCWDM | Local Municipalities: City of Mhlathuze LM, KCDM, | CoMLM to continue with WCWDM activities KCDM to continue with existing WCWDM programme | High priority, implementation to continue/start immediately CoM: 10% savings, reduction in growth by 2025 (6.3 million m3) KCDM: 15% savings, reduction in growth by 2025 (0.6 million m3)
Maintain existing Thukela Transfer scheme | MW | Maintain installed capacity | Immediate and ongoing (34 million m3/annum)

## Slide 36
Intervention | Primary Responsibility | Comments | Target Date (priority)
Complete Thukela Transfer upgrade from Middeldrift | DWS: RO NWRIB MW | The scheme was originally initiated as an emergency scheme. The initial urgency to implement should be maintained | High priority (December 2023) (34 million m3/annum)
Water Reuse | CoM LM | This intervention has been started. | Medium priority level (2032) (11 million m3/annum)
Interim Restriction Rule to Benefit Priority (Primary) Users | DWS: Directorate Water Resources Planning Systems | This study is underway | Immediate and ongoing
Efficient system operation | DWS RO | The existing system should not be allowed to fail, and should be expanded to additional key flow monitoring points throughout the catchments. It is specifically important to improve the flow monitoring in the tributary catchments upstream of the Mhlathuze weir in order to forewarn of water coming | Immediate and ongoing

## Slide 37
Intervention | Primary Responsibility | Comments | Target Date (priority)
Existing Dam Raising | DWS: OA |  | Low priority (2035) (5.8 million m3/annum)
New Dam Construction | MW | Tendering to be undertaken by implementing agent, Construction to be outsourced. | Low priority (dam construction) (2038) Medium priority (feasibility study) (12 million m3/annum)
Lower Thukela Transfer to KCDM | Umgeni Water | This study has been initiated and communication with the study team should be ongoing | High priority
Remove alien vegetation | Department of Environmental Affairs, Mhlathuze CMF | Focus on areas upstream of Dams and Lakes | Immediate and ongoing
Groundwater | Municipalities | Promote development of GW resources for local WSSs | As and when required

## Slide 38: WAY FORWARD
Water requirement projections and monitoring
Actual use: irrigation sector
Strasc coordination & implementation tracking

## Slide 39: IMPLEMENTATION AND MAINTENANCE OF THE WATER RECONCILIATION STRATEGY FOR RICHARDS BAY AND SURROUNDING TOWNS Strategy Steering Committee Meeting (SSC) 5 Item 9: Discussion Item 10: Communication Item 11: Closure