## Sheet1
Determination of Water Resource Classes, Reserve and Resource Quality Objectives Study for Secondary Catchments A5 – A9 within the Limpopo Water Management Area (WMA 1) and Secondary Catchment B9 in the Olifants Water Management Area (WMA 2)
ISSUES AND RESPONSE REGISTER
NUMBER | DATE COMMENT RAISED | COMMENT RAISED BY | COMMENT RAISED BY ORGANISATION | PLAFORM AT WHICH COMMENT RAISED | COMMENT RAISED | RESPONSE BY | RESPONSE | ACTION | ACTION TARGET DATE
1 | 2022-07-01 | D Olamiju | Limpopo Department of Public Works | Public Meeting #1 | In terms of the overview, she was not sure if Lebowa and Gazankulu was in terms of the Act, as these are not in current geographic delineations | PSP | Ms Mohapi indicated that reference was made to former homelands. It is acknowledged that these delineations are no longer in place.
2 | 2022-07-01 | Mhlarhi Nsovo | DWS | Public Meeting #1 | Questioned how the RQOs, Class and Reserve will be determined for the Nylsvley wetland while it is under the Ramsar Convention. She queried if there would be a partnership to determine, for example, the RQOs. | PSP | Ms Mohapi queried from M Nsovo what would prevent the RQOs being determined if the wetland is a Ramsar site since it would be strengthening the protection. Ms J Jay indicated that their Directorate within the DFFE, which is Water Sources and Wetland Conservation, is the focal point for the Ramsar Convention and going forward, one way to ensure the Ramsar requirements are incorporated is to ensure their Office and the management authority for the two Ramsar Sites are represented on the PSC.
4 | 2022-07-01 | T Rananga | DWS | Public Meeting #1 | Highlighted that since 2016/2017 there have been frequent floods, almost on a yearly basis. He queried if this would be taken into consideration in the modelling and hydrology. | PSP | K Reinecke responded indicating that the hydrology is being extended to capture the recent change in flood/drought conditions. He believes the hydrology will be extended to 2021.
5 | 2022-07-01 | B Weston | DWS | Public Meeting #1 | Queried if the six (6) groundwater sources mentioned in the presentation, include the Strategic Groundwater Sources. | PSP | M Holland confirmed that this was the case.
6 | 2022-07-01 | T Rananga | DWS | Public Meeting #1 | Recommended that the groundwater team speak to the municipalities regarding groundwater use. He indicated that relying on the National Groundwater Database can result in an underestimate of the water use figures. | PSP | The GW team will liaise with the municipalities on current groundwater use in their areas of responsibility. Ms Mohapi indicated that they will engage with the provincial DWS office to ensure a better participation of municipalities on this project. | DWS : Water Ecosystems Management & PSP (GW) | 2023-03-01
7 | 2022-07-01 | T Rananga | DWS | Public Meeting #1 | Mr Rananga raised the issue of recharge of groundwater systems and the pollution thereof, due to e.g., the use of Ventilated Pit Latrines. | PSP | Ms Mohapi indicated that the structures and platforms within the DWS need to address the matter of pollution of the groundwater.
8 | 2022-07-01 | T Rananga | DWS | Public Meeting #1 | Noted that there is approximately 3 million m3/a water available in the Doorndraai Dam. He will provide the dam capacity and storage to the PSP as well as the dam yields to enhance what is required. | PSP | The PSP will appreciate the information | PSP to follow up with Mr Rananga | 2023-03-01
9 | 2022-07-05 | Barbara Weston | DWS | PSC #1 | Organisations such as Sanbi and Mpumalanga Parks Board should be involved in the project. The Mpumalanga Parks Board (André Hoffman and Francois Roux) should participate as the study focuses on the Nyslvley wetland, which they know well. | PSP | Sanbi has been invited to participate. The project does not fall into the Mpumalanga Province and therefore the Mpumalanga Parks Board was not invited to participate on the project. André Hoffman and Francois Roux wil be invited to participate. | PSP to contact Mr Roux and Mr Hoffman | 2022-10-01
10 | 2022-07-05 | Leon Eksteen | Sterk River WUA | PSC #1 | Mr Leon Eksteen expressed concern as an agricultural water user in the Sterk River catchment on the widespread pollution in the area and the control of pollution. He would like to see some discipline to maintain the quality and the rules and regulations to ensure water for the future. | DWS & PSP | Mr Atwaru encouraged Mr Eksteen to express these views in the visioning form provided and to provide some guidance regarding his aspirations for the IUA. The PSP takes note of the water quality concerns in the catchment and will feed this into the Classification and RQO process. Mr Ramalobeng indicated that the DWS is currently monitoring nine dams for eutrophication and are looking to extend the monitoring to more dams in the area. This monitoring will provide valuable information on nutrient loads in the water resources. | PSP to take concerns regarding water quality concerns into Classification and RQO process | 2023-05-01
11 | 2022-11-21 | Anton Linström | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | A catchment prioritisation project for the Limpopo Province for wetland rehabilitation has been conducted. This specifically looked at the rehabilitation potential but also considered the diversity importance, the importance of wetland ecosystem services and people in livelihood importance. They have a variety of data layers, very much the same as what is being used for this project, but he believes it can add value. | J MacKenzie - PSP | The data and project reports will be valuable to the project and contact will be made with Mr Linström to acquire the information. | J MacKenzie | 2023-02-01
12 | 2022-11-21 | Jackie Jay | DFFE | Technical Task Group meeting #1 (Wetland prioritisation) | Wetlands might be particularly sensitive to water quality changes. There are some pans that are challenging to get back when the water quality changes. Is there a surrogate species that can be used, e.g., amphibians or a recommendation stating it cannot be done yet as there is no data available and make suggestions for future approaches? | J MacKenzie - PSP | Mr MacKenzie responded that he does not have water quality sensitivities built into the wetland prioritisation process, but will chat with Nico Rossouw, the water quality specialist on the group, to see how something can be built in as a measure of sensitivity to water quality changes. | J MacKenzie | 2023-02-01
13 | 2022-11-21 | Anton Linström | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | It is recommended that the groundwater and surface water strategic water source areas in terms of water availability are considered in the wetland prioritisation process, as they did look at this to prioritise wetland rehabilitation. | J MacKenzie - PSP | Mr MacKenzie noted that he looked at this, but there were many missing values that it was not taken further. | Mr MacKenzie and Mr Linström to discuss the methodology used and how the missing data was handled. | 2023-02-01
14 | 2022-11-21 | Eddie Riddell | Sanparks - KNP | Technical Task Group meeting #1 (Wetland prioritisation) | Some potential gaps in the wetland prioritisation that can be considered include: (i) In Mapungubwe, the ephemeral Samaria wetland, which is on communal land between the two parts of the Park. (ii) The Malahlapanga site in the Kruger National Park. The peat dome system is part of a complex – The Malahlapanga is the main system, with the Mfayeni in the Park and the Baleni springs on the Klein Letaba. The latter is in B8 (outside the study area), but it is part of the peat dome complex at a larger scale and probably linked to an artesian process. |  |  | MacKenzie to address the suggestions in the wetland prioritisation process | 2023-02-01
15 | 2022-11-21 | Eddie Riddell | Sanparks - KNP | Technical Task Group meeting #1 (Wetland prioritisation) | There is a process underway of naming the individual pans in the Makuleke. They are doing away with the Western names and re-naming in Tsonga. These name changes must be noted, especially during the gazetting process. The information sheet for the Makuleke will soon be available. |  |  | E Riddell has provided Makuleke information (Kmz of the pans and names) to the study team | The new names of the pans have been received 19 December 2022.
16 | 2022-11-21 | Anton Linström | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | Mr Linström contributed to the list of important sites for wetland prioritisation, which included: (i) Nyl River floodplain (ii) The eye of the Nyl. There are peatlands in the area, and the area is threatened. Some rehabilitation work has been conducted in the area. (iii) Wonderkrater wetlands outside of the Nyl floodplain. It has a thermal signature. A detailed assessment has been conducted for the rehabilitation plan. (iv) On the Soutpanesberg, east of Louis Trichardt, is the Juma area, which has beautiful peatlands. (v) Mutale at the inflow to Lake Fundudzi are some peatlands, and in the area upstream into the forested area are some important systems, including peatlands and seeps. (vi) Mapungubwe – the floodplain area in the lower reaches of Kolope, have already been assessed and described in a wetland rehabilitation plan. (vii) In the Mapungubwe's priority area, the ZZ2 is draining the river itself, which has a catastrophic effect on the riparian areas. (viii) Thermal eyes in the Kruger National Park. Several studies have been done on these, such as groundwater and riparian vegetation studies and rehabilitation plans. (viii) Blouberg area, which is to the west of the Soutpanesberg. This area will be focused on soon by Working for Wetlands |  |  | MacKenzie to address the suggestions in the wetland prioritisation process | 2023-02-01
17 | 2022-11-21 | Gary Marneweck | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | Mr Marneweck noted the importance of the following: (i) Nyl pans. The pans are likely important from a functional perspective because they receive treated sewage discharge and are therefore likely to be important for water quality enhancement at the lower end of the system. (ii) Soutpanesberg plateau. The area is important from a biodiversity and wetland perspective, with some unique aspects of both. (iii) Blouberg area, which is to the west of the Soutpanesberg. It is a free-standing system and is a centre of endemism. (iv) The tributaries the feed the Mogalakwena River from the Waterberg area |  |  | MacKenzie to address the suggestions in the wetland prioritisation process | 2023-02-01
18 | 2022-11-21 | Adaora Okonkwo | DWS | Technical Task Group meeting #1 (Wetland prioritisation) | Ms Okonkwo queried whether areas of groundwater interaction were considered in the wetland prioritisation process. She indicated that while these areas may not be a high priority for the wetland component, they may be a high priority from a groundwater perspective. When RQOs are set, there must be something from wetlands and groundwater. | J MacKenzie - PSP | Mr MacKenzie mentioned that he and Dr Holland (the groundwater specialist on the team) are in liaison and have been looking at groundwater contribution to wetlands. However, they would take another look at the contribution of wetlands to groundwater. The groundwater team is busy with the groundwater prioritisation areas, and there is time to look at the groundwater priority areas in terms of the wetlands in the area and their functions. | J MacKenzie | 2023-02-01
19 | 2022-11-21 | Lindley Itimu | Pegasys | Technical Task Group meeting #1 (Wetland prioritisation) | Pegasys worked on the Pafuri-Sengwe node, where the Mutale wetlands are situated. There were groundwater interactions in this area. Mr MacKenzie to refer to the report they compiled for more detail. | B Weston - DWS | Mrs Weston indicated that this report was provided to Ms Thenga. However, she requested Ms Thenga to check with Mr Itimu if it is the correct report before sending it out to the team. | V Thenga | 2023/01/01 Reports received 10 March 2023
20 | 2022-11-21 | Jackie Jay | DFFE | Technical Task Group meeting #1 (Wetland prioritisation) | J Jay queried if the shapefiles and excel tables supporting the reporting process would be made available to the public. | B Weston - DWS | Mrs Weston responded by saying as far as she is aware, once the information is gazetted, it will be made publicly available on the DWS website. The DWS will hold the micro-data, shape files, and technical information to support the gazette information to give it validity and technical leverage should the results be contested.
21 | 2022-11-21 | Jackie Jay | DFFE | Technical Task Group meeting #1 (Wetland prioritisation) | Ms Jay then requested the DWS to provide further direction on where they can access the shapefiles emanating from the various classification studies. | A Okonkwe - DWS | Ms Okonkwe provided guidance on acquiring the data from the classification studies. She explained that the DWS would hold the data once the project had been completed. Requests for this information can be made through the DWS project managers. A simple process needs to be followed. A form must be completed and signed indicating that the data will not be used for profit.
22 | 2022-11-21 | Jackie Jay | DFFE | Technical Task Group meeting #1 (Wetland prioritisation) | Ms Jay queried access to the DTM data purchased from GeoSmart (Stellenbosch). | J MacKenzie (PSP), B Weston, Y Atwaru (DWS) | Mr MacKenzie indicated that there might be restrictions to the data usage on a broader scale, and the contract will need to be reviewed. Mrs Weston and Mr Atwaru indicated that data purchased with project funds resides with the DWS. This is to be discussed internally. | DWS & PSP | 2023-03-01
23 | 2022-11-21 | Eddie Riddell | Sanparks - KNP | Technical Task Group meeting #1 (Wetland prioritisation) | Mr Riddell acknowledged that this is great work being done and will be valuable over and above the classification process. He indicated the need to discuss the principles of using the information moving forward. With the Kruger National Park being part of the Greater Transfrontier Park, they are internationalising their Freshwater Ecosystem work. Many projects are helping them support this. Pegasys is a service provider helping the Park in some of these studies. One of the critical spin-offs will be to allow access to the data in a transboundary context because you will not only be modelling the flood levels on the South African side only. It would have relevance for the Zimbabwe and Mozambique side in terms of linking to the Limpopo flood forecasting system. Mr Riddell recommended the DWS chat with the relevant Directorates doing this work. Resilient Waters is also helping the Limpopo Watercourse Commission with a flood forecasting system. Making these linkages will help strengthen the impact of this work and have a crucial benefit. |  | Mrs Weston acknowledged this and indicated this would also need the involvement of other departments. | DWS Management to liaise with International Water Departments | DWS to provide a date
24 | 2022-11-21 | Gary Marneweck | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | In some Reserve studies it was found that there were wetlands below outlets from sewage works that did not come up as priority systems from a biodiversity or other perspective analysed or considered. However, these were identified as possibly being important from a functional perspective, especially in respect of possible water quality improvement. These may therefore be important in the larger system context. |  |  | MacKenzie – to include coverage of sewage treatment works | 2023-02-01
25 | 2022-11-21 | Gary Marneweck | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | There is a lot of information on the Nyl River floodplain and that Mr MacKenzie is welcome to contact him, should he be able to contribute in this regard. |  |  | MacKenzie to liaise with Mr Marneweck
26 | 2022-11-21 | Anton Linström | Wetland Ecologist | Technical Task Group meeting #1 (Wetland prioritisation) | There are many plans for mining in the area, which can threaten the systems we are focusing on. It would be essential to take such developments into account. | B Weston - DWS | Mrs Weston indicated that this would be considered in the classification process; however, scenarios are also looked at in the Reserve process in terms of how the plans affect achieving the recommended ecological category. She addressed the DWS regional personnel to emphasise the importance of providing the team with every significant development proposed in the study area. These will need to be assessed to meet the ecological targets and objectives. Also, if these developments are implemented, there is a need to consider rehabilitation and restoration when looking at the implementation plan. She also mentioned that there would be a need to check with the Planning Directorate of the DWS on the Reconciliation Strategies currently being undertaken and if they are aware of significant, proposed developments in the area. | Project team to liaise with Region and Planning Directorates on planned developments | 2023-06-01
27 | 2022-11-21 | Barbara Weston | DWS | Technical Task Group meeting #1 (Wetland prioritisation) | To ensure implementation of the outcomes of this study, consideration should be given to forming partnerships with other organisations such as Environmental Affairs, Agriculture, and non-governmental organisations |  |  | DWS management and inter-departmental discussions | DWS to provide a date
28 | 2023-06-09 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Tendani Nditwani queried the use of CHIRPS in areas of missing data. He indicated that on the update of the Reconciliation Strategy in the North, they were advised not to use the CHIRPS data as there were aspects that the hydrologist did not support on CHIRPS. He elaborated that they were informed that if they used the CHIRPS data, upon review of the results, they would be found wanting in confidence. For this reason, they had to wait about a year for the SAWS data. He asked Mr Howard to share if he had any reservations or challenges in using the CHIRPS data. | G Howard & K Reinecke | Mr Howard responded that he had used CHIRPS extensively all-around Africa. It does not work in some places, while in others it does. He highlighted that the CHIRPS generally produces much more low rainfall days than recorded. For example, no rainfall can be recorded at a rainfall gauge, but CHIRPS will give 3mm. He explained that before using the data, the CHIRPS data needs to be bias-corrected. In other words, if the January mean is more than what you are getting out at an observed point rainfall station, you adjust all the values to return to the mean of the observed record.
He agreed that using the point rainfall data and having SAWS data is better. However, for this study, CHIRPS will be sufficiently accurate because the environmental flow analysis is based on long records. For this study, the monthly data are from 1920 to 2020, with CHIRPS taking it from 2010 to 2020. The hydrology was extended to include the drought in the Limpopo area around 2015-2017. Most of the analysis (on the daily flows) uses an exceedance curve, i.e., the percentage of time a flow is exceeded. Overall, the long-term statistics will drive the RQO analysis, and those will not be altered significantly by including CHIRPS.
Dr Reinecke highlighted that in terms of the environmental flows, the focus is always on long-term statistics. He agreed with Mr Howard that the last piece of the record is inconsequential in affecting the long-term statistics (i.e., the averages and medians). Dr Reinecke indicated that Mr Nditwani is correct that there will be (and always is) challenges to modelled hydrological data. However, we need to do our best with the lack of gauging stations and gauging stations in poor condition.
Mr Howard summarised the discussion should there be criticism raised for the project in using CHIRPS as follows: (i) The environmental flow specialists do not use the time series but the statistics, so it is the mean, standard deviation, coefficient of deviation and so forth. The ten years of CHIRPS data used will disappear into 100 years, and the statistics will change by literally 1%. (ii) the CHIRPS data was bias-corrected, so it does have similar statistics to the observed records.
29 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Include Susandal Dam downstream of Vischgat Dam on the map |  | Included and updated GIS to reflect dams | T Tlou - to include the dam onto the map | 2023-07-01
30 | 2023-06-09 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Lephalala catchment, the 2010 records showed large use, approximately 42 million m3/a on surface water use. He noted however, that this might have changed since. | T Tlou | The current irrigation use provided was 1.2 million m3/a. Mr Tlou will need to investigate the large use that Mr Nditwani noted. | Upon investigation it was noted that the 42 million m3/a irrigation use exists and the spreadsheet was updated accordingly | 2023-07-01
31 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | A small dam, in the Nyl/Sterk IUA, called the Gert Combrink Dam, supplies water to Mokopane. During the 2015/2016 Operating Analysis, it was recorded to provide around 3.2 million m3/a to Mokopane Town |  | Included and updated GIS to reflect dams | T Tlou - To update the spreadsheet | 2023-07-01
32 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Rananga indicated that there was a 1.8 million m3/a allocation from Donkerpoort Dam to Modimolle irrigation. |  | Where dealing with water requirements and not allocations. The water requirements were included | T Tlou - To update the spreadsheet | 2023-07-01
33 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Rananga mentioned that Lepelle Northern Water plans to increase their package plant's size from 4.9 to 6.2 million m3/a. This will be a future demand from Doorndraai Dam. |  | Spreadsheet dealt with requirements not the resource. Was projected in the future water requirements. | T Tlou - To update the spreadsheet | 2023-07-01
34 | 2023-06-09 | Toriso Tlou | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Tlou requested confirmation of the amount of 4.38 million m3/a to Mokopane Town and surrounds from Flag Boshielo Dam. He explained that this information was obtained from Lepelle Northern Water but would like confirmation from the DWS. | C Ntuli T Rananga | Ms Ntuli indicated that this could be a future demand, as she was unaware of this. Mr Rananga stated that he did not have this information but would check on this. | T Rananga | 2023-07-01
35 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Rananga indicated that on the Glen Alpine irrigation, there had been indications of high losses of 78%. He questioned whether this should be reflected as a requirement. When operating the system, they account for the losses and release more than 7.3 million m3/a. | T Tlou | Mr Tlou indicated that the river losses were not considered
36 | 2023-06-09 | Celiwe Ntuli | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Ms Ntuli indicated that the 3.34 million m3/a for domestic use in the Mogalakwena is an allocation, but it is not part of the system's operation. Perhaps this amount is included in the releases for the irrigation sector? | T Tlou T Rananga | Mr Tlou indicated that the domestic allocation is being released through the irrigation scheme, according to the figures received from the Scheme. Mr Rananga mentioned that in 2019 they attended a community meeting where domestic water was requested from Glen Alpine Dam. Likely, this has since been included; however, he will confirm this. | T Rananga | 2023-07-01
37 | 2023-06-09 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Nditwani requested Mr Rananga provide the updated transfers from Ebenezer, Dam Naude and Flag Boshielo Dams into the Sand catchment. | T Rananga | Mr Rananga confirmed the Ebenezer allocation as 16.2 million m3/a. Although the allocation from Dap Naude Dam is 6.53 million m3/a, they are using around 4 million m3/a. Mr Rananga to provide the water allocation figures and the SOF presentations. This information has been provided to the team. | T Rananga | 2023-07-01
38 | 2023-06-09 | Refilwe Mothiba | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Ms Mothiba noted that the Nancefield Oxidation Ponds are operating in Musina Town. Ms Mothiba indicated that they are discharging into the Malela River, which flows into the Limpopo River. | T Tlou | Mr Tlou indicated that these oxidation ponds were not included as they have no return flow. Mr Tlou noted that he would check on these discharges. - Evaporation ponds confirmed by Green Drop assessment. Evaporation ponds | T Tlou | 2023-07-01
39 | 2023-06-09 | Rufus Nengovhela | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Nengovhela mentioned a registered allocation of 10.5 million m3/a to Musina Town from groundwater. This is their current water use granted in June 2023. |  | Spreadseet deals with water use and requiements. Not allocations. The allocation was included | T Tlou - To update the spreadsheet | 2023-07-01
40 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Rananga suggested the Masheshane and Houtrivier Dams be included on the Sand River. |  | was updated | T Tlou - To update the spreadsheet | 2022-07-01
41 | 2023-06-09 | Rufus Nengovhela | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Nengovhela noted that the Nwanedi catchment was not included on the spreadsheet. | T Tlou | The Nwanedi information was omitted by error on this spreadsheet, when the information was being carried over. It will be reflected. | T Tlou | 2023-07-01
42 | 2023-06-09 | Rufus Nengovhela | DWS | Technical Task Group meeting #2 (Operational Scenarios) | He highlighted that there is much agriculture along the Nwanedi River, and the area has been earmarked by the Department of Agriculture. | T Tlou | Mr Tlou asked if the DWS could assist in obtaining the locations of future agricultural development from the Department of Agriculture. | R Nengovhela | 2023-07-01
43 | 2023-06-09 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Nditwani noted that the allocation toward livestock is significant in the Nzhelele catchment of this size and should be noted. |  | Livestock water use was included in hydrology model. | T Tlou to include the livestock water requirements in the spreadsheet | 2023-07-01
44 | 2023-06-09 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Nditwani indicated that Tshifire Murunwa WTW may be an additional user in the headwaters of the Nzhelele River. The dam was initially used for afforestation and thereafter for domestic purposes. |  | Additional users factored in current and future water requirementss | T Tlou - To update the spreadsheet | 2023-07-01
45 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Rananga noted that there may be an underestimation of the allocations in Collins Chabane LM (Upper Luvuvhu). He indicated that he would provide the team with the 2019 site report. |  |  | T Rananga | 2023-07-01
46 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Rananga requested that the Nwanedi-Luphephe WTW be included |  | was included in the spreadsheets | T Tlou - To update the spreadsheet | 2023-07-01
47 | 2023-06-09 | Rufus Nengovhela | DWS | Technical Task Group meeting #2 (Operational Scenarios) | Mr Nengovhela queried if the irrigation schemes along the Luvuvhu and Mutale systems have been included. He mentioned that there are several of these schemes and along the Luvuvhu River, there are large individual farmers. | T Tlou | Mr Tlou indicated that he did not exclude these schemes but did not have this information. He requested the DWS to assist with this information. | R Nengovhela | 2023-07-01
48 | 2023-06-09 | Thomas Rananga | DWS | Technical Task Group meeting #2 (Operational Scenarios) | It was noted that the area down to the Makuleke needs to be considered in terms of the water requirements as it is within the study area as well as the Shingwedzi |  | Included Makuleke and Shingwedzi | T Tlou - To update the spreadsheet | 2023-07-01
49 | 2023-06-09 | Toriso Tlou | Myra Consulting | Technical Task Group meeting #2 (Operational Scenarios) | Mr Tlou requested confirmation from the DWS that there is no potential growth in the mining sector or for exploration in this catchment. |  |  | H Rananga / T Nditwani | 2023-07-01
50 | 2023-06-09 | Toriso Tlou | Myra Consulting | Technical Task Group meeting #2 (Operational Scenarios) | Mr Tlou mentioned the SEZ northside development in the Musina area and requested confirmation from Mr Nditwani of the possibility of developing a dam or off-channel storage within the Lower Sand River. | T Nditwani | Mr Nditwani confirmed that they are looking at two dam sites. One is off-channel storage, capturing water from the Sand and the Limpopo River. The other dam is on the Mutale system. Mr Nditwani will provide the preliminary numbers; however, these need to go to feasibility. | T Nditwani | 2023-07-01
51 | 2023-07-21 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) - Technical Notes | Requested clarity on the study area boundaries as the Development Scenarios report states that the Musina Dams to supply the SEZ are located below the last node in the study area and need not be modelled. | A Singh | The study area comprises secondary catchments A5 (Lephalale), A6 (Mogalakwena), A7 (Sand), A8 (Nzhelele), A9 (Levuvhu) and B9 (Shingwedzi) from source to their confluence with the Limpopo River. The reason for not modelling the proposed dams for the SEZ in Musina, was that these dams fall below our last EWR site, which is approximately 11km from the confluence of the Sand River with the Limpopo River. The last node will provide the ecological water requirements of the river reach to the confluence with the Limpopo. As we understand these dams are pumped storage schemes supplied with water from the Limpopo River, upstream of the confluence with the Sand. Since these proposed off-channel dams are very close to the confluence with the Limpopo River and are not taking runoff directly from the Sand River, the ecological water contribution to the Sand River should not be affected.
52 | 2023-07-21 | Tendani Nditwani | DWS | Technical Task Group meeting #2 (Operational Scenarios) - Technical Notes | This was a follow on statement to the response in point 51. The Sand River Dam is to be located on the Sand River before the confluence and there will be flows from Sand River upstream into that dam. | A Singh | She thanked Mr Nditwani for the clarification regarding the Sand River Dam. The team will liaise with respect to addressing the proposed Dam in the future development scenario. | Study team to liaise on addressing the dam in the future development scenarios | 2023-10-01
53 | 2024-04-14 | Barbara Van Koppen | International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Comment on the method: The method to assess the BHNR expands the method proposed in King and Pienaar (2011) by including the Community Survey and the provincial Census summary statistics. As such this can be an important step forward. However, the report remains unclear on how the categorization in the Census fits the crucial distinction between formal public systems and informal self-supply – for which the BHNR is most important. As almost any access to water is a matter of depending on surface or groundwater, that category fails to clarify. For example, boreholes can be publicly installed or private property of a household or self-organized collective. Moreover, the Census data may include main water sources – assuming that they are 24/7 and year-round functional. Yet, most self-supply households combines various water sources, depending on availability, costs, season, etc. At least, these weaknesses should be transparent, and recommendations made on further work needed. | Jane Turpie | Thank you we have added some discussion on this. | Revisions to BHN report | 2024-04-01
54 | 2024-04-14 | Barbara Van Koppen | International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Comment on the method: The problem of dwindling if not ephemeral streams (or aquifers) is not addressed, even though the study area comprises a nearly 50 percent split between perennial and ephemeral rivers. Yet, dry seasons and droughts are the vital periods for the state to ensure a highest priority for basic human needs. This problem should have been flagged with recommendations on next steps | Jane Turpie | Yes, but BHN does not extend to providing flows when they would not occur naturally, it is a matter of ensuring that others are not withdrawing the flows (that do exist) that are needed for BHN. | Revisions to BHN report | 2024-04-01
55 | 2024-04-14 | Barbara Van Koppen | International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Quantifying the BHN: The report proposes a BHNR of 50 lpcd. This better reflects realities than the 25 lpcd (often confusing with the state’s commitment to water infrastructure of at least 25 lpcd). However, for the following reasons even 50 lpcd is still too low. The definition is: “BHNR provides for the essential needs of individuals served by the water resource in question and includes water for drinking, for food preparation and for personal hygiene”. Even for just domestic water uses, the international guideline is 120 lpcd, whereas South Africa’s average is even higher. Even 50 lpcd widens the relative inequalities. Moreover, in low-income rural areas, where self-supply is most common and the BHNR most needed, several joint studies by the Department of Agriculture, Land Reform and Rural Development, the Water Research Commission and the International Water Management Institute found the following: * even at 20 lpcd, self-supply is not restricted to domestic uses, but water for livestock, gardens or small irrigated plots has a higher priority than luxury domestic uses (e.g., daily bathing, laundry at home, etc). These productive uses with a higher priority than common domestic uses entirely fit the Constitutional Section 27 stipulating that everyone has a right to sufficient water and food. http://wrcwebsite.azurewebsites.net/wpcontent/uploads/mdocs/TT%20840%20final%20web.pdf *As modern remote sensing technologies show, informal irrigation is widely spread in former homelands. In particular: out of all 110,610 cropped area in former Venda, 50426 ha (s 46%) was irrigated in the winter of 2015. See http://www.iwmi.cgiar.org/Publications/Working_Papers/working/wor174.pdf. These small-scale uses meet basic human needs or are otherwise defined as high priority. Most fall under Schedule One’s ‘subsistence uses’, which are defined as: ‘reasonable domestic use [. . .] small gardening not for commercial purposes and the watering of animals excluding feedlots [. . .]. These uses unambiguously fit Constitutional rights as Basic Human Needs. If contested, or for higher quantities, the prioritization of the legally binding National Water Resources Strategy – 3rd edition would accord the 3rd highest priority to these uses, defined as: Water resources that contribute to poverty eradication, livelihoods and racial and gender equity. This priority comes after (1) Reserve, consisting of the Ecological Reserve and Basic Human Needs Reserve, and (2) International obligations. However, these priority 3 uses are a higher priority than priority (4) Strategic uses and (5) Licenced uses for general economic purposes, such as large-scale commercial irrigation, forestry, mining and industries, using high volumes and seriously polluting, so with high impacts on other water users and the Ecological Reserve. | Jane Turpie | Following feedback from DWS we were asked to amend our calculations to use 25 litres. However we have kept the comment that international recommendations are for a higher allowance. BHN doesn’t make provision for informal irrigation, it is for domestic use, perhaps including a small house vegetable garden. It does raise an important issue that perhaps small-scale irrigation needs to be accounted for overtly. We have added a comment on this. | Revisions to BHN report | 2024-04-01
56 | 2024-04-14 | Barbara Van Koppen | International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | The report rightly states: “Water for basic needs that is accessed directly from ecosystems needs more protection as there is poor control and monitoring of whether or not it is indeed available”. This holds for all above mentioned uses. In order to ensure more effective control and monitoring, these constitutional commitments should be expressed in the practical and betterknown terms of “assurance of supply” | Jane Turpie | Good point, thank you. Added that in the text. | Revisions to BHN report | 2024-04-01
57 | 2024-04-14 | Barbara Van Koppen | International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | King and Pienaar (2011) recommended: “Because of the weakness in the current approach for setting the BHNR (Chapter 5), the methods currently in use need to be reviewed to produce a consistent approach and formal guidelines”. These comments highlight the urgent need to continue with that. | Jane Turpie | Noted, thanks. No change required. However just to add that we are going to be ensuring that the BHN is more accurately considered in hydro models (as a withdrawal) than in previous classification studies. | Revisions to BHN report | 2024-04-01
58 | 2024-04-22 | Lauren Liebenberg | Living Limpopo, the International Water Management Institute (IWMI), herein represented by Professor Emeritus, Dr Barabara von Koppen (PhD), the Association for Water and Rural Development (AWARD) and the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and its members, including Dzomo La Mupo and The Herd Nature Reserve, herein represented by Dr Victor Munnik (PhD), | Comment on the EWR and BHNR reports (PSC2) | We record that we are concerned that the determinations for these water resources may serve to sanction grossly irresponsible water resource management decisions connected in particular, to the Musina-Makhado Special Economic Zone and expansion of coal mining in the region. | Adhishri Singh | The classification of the water resources and the scenario analysis has not commenced yet. The development of scenarios will begin soon, which is why your vision and aspirations need to be communicated to us on the visioning forms. The scenarios will include ecology and economic-driven scenarios and a combination of these to provide a spatially distributed solution where different priorities can be recognised in different parts of the study area. The proposed classification configuration for the study area will be developed in consultation with stakeholders.
59 | 2024-04-22 | Lauren Liebenberg | Living Limpopo, the International Water Management Institute (IWMI), herein represented by Professor Emeritus, Dr Barabara von Koppen (PhD), the Association for Water and Rural Development (AWARD) and the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and its members, including Dzomo La Mupo and The Herd Nature Reserve, herein represented by Dr Victor Munnik (PhD), | Comment on the EWR and BHNR reports (PSC2) | We urgently request an extension of the deadlines for stakeholders to submit a Visioning Form and to comment on the voluminous technical reports published on the “Luvuvhu Classes, Reserve and RQOS” project page on the DWS online portal, | DWS | The Department has agreed to extend the comment period on the Project Technical reports and the submission of the Visioning Form to 17 May 2024
60 | 2024-04-22 | Lauren Liebenberg | Living Limpopo, the International Water Management Institute (IWMI), herein represented by Professor Emeritus, Dr Barabara von Koppen (PhD), the Association for Water and Rural Development (AWARD) and the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and its members, including Dzomo La Mupo and The Herd Nature Reserve, herein represented by Dr Victor Munnik (PhD), | Comment on the EWR and BHNR reports (PSC2) | Request another opportunity to meet with the Project Steering Committee to discuss our concerns and participate more meaningfully in the economic development scenario planning and evaluation process | Adhishri Singh | The classification of the water resources and the scenario analysis has not commenced yet. The development of scenarios will begin soon, which is why your vision and aspirations need to be communicated to us on the visioning forms. The scenarios will include ecology and economic-driven scenarios and a combination of these to provide a spatially distributed solution where different priorities can be recognised in different parts of the study area. The proposed classification configuration for the study area will be developed in consultation with stakeholders.
61 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | As the Reserve study of these secondary catchments of the Limpopo-Olifants WMA for the Reserve determination confirms, the “water resources are heavily stressed due to increased development”. Yet litle to no real improvement in their condition is recommended in the Ecological Water Requirement (EWR) report, despite the fact that improvement is both feasible and desirable, including to support economic growth and development where such development is nature-based. | Adhishri Singh | The Recommended Ecological Category (REC), which has been determined and reported on in the EWR Rivers Report series is the recommendation for the river reach represented by the EWR site, based on the present ecological condition, the Ecological Importance and Sensitivity and an assessment of possible improvements (flow and non-flow related). Further improvements in ecological condition of the water resources will be considered in the scenario analysis process.
62 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | The Reserve determination is proceeding in the context of government-supported plans to expand coal mining and develop the heavy industrial zones of the Musina-Makhado Special Economic Zone (MMSEZ), which will have outsized impacts on water resources of the Limpopo WMA and the resilience of the entire Limpopo River Basin system | Adhishri Singh | Developments driven by government or any other sector will not guide the classification but will be an input into the classification process. The implications of the coal mining expansions and the development of the heavy industrial zones of the MMSEZ, together with developments identified in other catchments will be determined accordingly in the various scenarios to be developed. The impact of the latter on meeting the Recommended Ecological Category and ultimately the Ecological category will be assessed and the risks documented.
63 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | The DWS has given repeated public assurances of its support for the expansion of mining, its commitment to the MMSEZ megaproject and to ensuring that its vast water requirements are met. | Adhishri Singh | Developments driven by government or any other sector will not guide the classification but will be an input into the classification process. The implications of the coal mining expansions and the development of the heavy industrial zones of the MMSEZ, together with developments identified in other catchments will be determined accordingly in the various scenarios to be developed. The impact of the latter on meeting the Recommended Ecological Category and ultimately the Ecological category will be assessed and the risks documented.
64 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | The scenario modelling undertaken to assess the impact of the development of the Greater Soutpansberg Coalfield and coal-based industry on the scale planned in the SEZ, purports to show that their impact on the affected catchments will be negligible or even positive. This is partly enabled by: A. the avoidance of a full-impact, worst-case scenario assessment of the water deficit exposure of the water demands of these planned mining and industrial projects in the already-stressed catchments in which they will be located, and partly by B. the complete disconnect between the assessment of secondary catchments i.e. tributaries of the Limpopo River and the Limpopo River mainstem within the scope of the Reserve study and the failure to recognise impact at a basin level. | Adhishri Singh | It must be pointed out that although the study area covers secondary catchments A5-A9 within the Limpopo basin, the Limpopo River is a transboundary resource which involves four countries and therefore it is within the mandate of the Limpopo Watercourse Commission (LIMCOM). The LIMCOM is currently conducting the E-flows study that is focussing on the Limpopo River including its major tributaries. Sharing of information between the studies is taking place.
65 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | The Reserve determination process is also proceeding in the absence of a functioning Catchment Management Agency (CMA) for the affected catchments, which is only now being established (in the form of the Limpopo-Olifants Catchment Management Agency (LOCMA)). Based on the record of the proceedings, it appears that DWS is over-represented on the Project Steering Commitee, which has a dominant role in the Reserve determination process, and it is not clear that there has been adequate water-user and other stakeholder consultation as provided for in the Regulations and Technical Guidelines for the Establishment of a Water Resource Classification System5 . | Adhishri Singh | In the absence of a functioning Catchment Management Agency (CMA), the DWS Regional Office assumes the role of the proto-CMA. Despite this, the classification process will strive to consult widely and ensure a reasonable public participation process. Conducting a Reserve is not subject to the establishment of a CMA.
66 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | Finally, we note that the MMSEZ SOC (Musina-Makhado Special Economic Zone State-Owned Company) has applied for a water use license for the ‘Phase 1’ water requirements of the energymetallurgical zone (EMSEZ) South Site – abstraction of groundwater in the Sand River-Nzhelele catchment. On 15 April 2024, the appointed Environmental Assessment Practitioner (EAP), Matukane & Associates,re-launched the suspended public participation process for the Water Use License Application (WULA). Considering the threat that the MMSEZ represents to the resilience of the entire Limpopo River Basin and all water users dependent on the water resources, the imperative of giving effect to the legitimate principles of the Reserve has never been greater | Adhishri Singh | We have taken note of the MMSEZ water use licence application, which will be included in the classification process, as part of the scenario analysis process.
67 | 2024-04-22 | Lauren Liebenberg | Living Limpopo | Comment on the EWR and BHNR reports (PSC2) | Considering the interests we collectively represent, and the significant and far-reaching implications of the Reserve for the environment and societal wellbeing, a failure to provide for a proper opportunity to consider and comment on the study reports and to contribute to the scenario development and evaluation process, would undermine the right to an adequate, fair and reasonable public participation process, as enshrined in Section 33 of the Constitution of the Republic of South Africa, 1996, and as embodied in the participatory principles underpinning the National Water Act, 1998. Please consider our request to extend the window for comment and for a further meeting to develop and evaluate alternative scenarios with regard also to the interim comments submited by Living Limpopo, IWMI and the Sand-Nzhelele-Luvuvhu WRRF. | Adhishri Singh | The classification of the water resources and the scenario analysis has not commenced yet. The development of scenarios will begin soon and will include ecology and economic-driven scenarios and a combination of these to provide a spatially distributed solution where different priorities can be recognised in different parts of the study area. The proposed classification configuration for the study area will be developed in consultation with stakeholders. An extension to the comment period has been provided to the 17 May 2024.
68 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Inadequate representation in the Reserve determination process. We record that we are concerned that there has been inadequate stakeholder representation and participation in the Reserve determination process to date. We were not aware of, nor attended either of the meetings that took place in 2022, and in light of the information shared in the BIDs and minutes, we request the following information regarding the PSC establishment and stakeholder engagement: 1. Who are the members of the PSC and what sectors or interests do they represent? | Adhishri Singh | The stakeholder database is provided on the DWS Website. The sectors include Government (National, Provincial and Local); Agriculture, Mining, Industry, Power, Catchment Management Forums, Water User Associations, Water Boards, Transport, Education, Research, Conservation and Environmental bodies, Traditional Leaders. All sectors are invited to Project Steering Committee (PSC) meetings. Should you feel there is a sector missing, please provide their details so we can update the database.
69 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | 2. Who nominated each member and who attended the public meeting on 12 May 2022? | Adhishri Singh | The attendance register for the public meeting is included in the minutes of the meeting, which is uploaded on the DWS project website.
70 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | 3. According to the notice published in the Zoutpansberger on 29 April 2022, two initial public meetings were scheduled to take place – in Thohoyandou on 12 May 2022 and in Mokopane on 13 May 2022 at venues to be confirmed on registration of interest. a. Please advise whether any other notice of these meetings was given. b. Please share the attendance register of the two public meetings and the minutes of each. | Adhishri Singh | The project and public meeting notices were published in the Bosveld Review, Limpopo Mirror (Zoutpansberger) and Mogol Post. Radio adverts went out on Phalaphala and Thobela from 5-11 May 2022. Further direct invitations were sent to identified stakeholders in the study area. Due to no stakeholders indicating interest to attend the public meeting in Mokopane in person, only one public meeting, which was a hybrid session to allow stakeholders from across the study area to participate, was held in Thohoyandou. The minutes from this meeting, including the stakeholder sectors invited and those that attended and the Issues and Response Register are provided on the DWS website
71 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | When will the full stakeholder register and Comments and Responses report be made available? | Adhishri Singh | The Stakeholder register and the Comments and response register has been uploaded to the DWS Website.
72 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | What visions were expressed by the PSC members “afforded the opportunity to express their vision for each IUA on the 5th July 2022 [meeting]”? | Adhishri Singh | The call for stakeholder visions has been extended to the 17 May 2024 and will be shared during the stakeholdr consultation process.
73 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | How have the different and potentially competing visions of “all major sectors and interests within the study” which must be represented on the PSC been incorporated into the scenario modelling? | Adhishri Singh | The scenario development and evaluation process is only now commencing. The proposed classification configuration for the study area will be developed in consultation with stakeholders.
74 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Please share the details of the stakeholder engagement plan, the stakeholders targeted and the platforms used. | Adhishri Singh | The stakeholder engagement plan and stakeholders targeted are on the DWS Website.
75 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | However, we submit that stakeholders who collectively represent an adequately diverse cross-section of water users, sectors and interests have not been given sufficient access to information, nor afforded sufficient time to review the information shared in the technical reports that have been made available by DWS and Myra Consulting, nor to have been afforded an adequate opportunity to contribute to scenario planning, nor to have been meaningfully consulted. We request an opportunity to interrogate more fully the economic development scenario that has been modelled, and to present and discuss alternative, more sustainable economic development scenarios than can adequately be articulated in, or modelled from, the 11 questions in the 3-page Visioning Form questionnaire. | Adhishri Singh | The classification of the water resources and the scenario analysis has not commenced yet and that many of your comments and concerns raised pre-empt this process. The development of scenarios will begin soon, which is why we requested your vision and aspirations to be communicated to us on the visioning forms. The scenarios will include ecology and economic-driven scenarios and a combination of these to provide a spatially distributed solution where different priorities can be recognised in different parts of the study area. The proposed classification configuration for the study area will be developed in consultation with stakeholders. For now, we have completed the determination of the Ecological Water Requirements (EWR) and the Basic Human Needs (BHN) requirements. For this, we have determined the Present Ecological State (PES) and the Ecological Importance and Sensitivity (EIS). We also assessed the river reach in terms of possible improvements that were not flow-related before recommending an Ecological Category or condition for the river reach represented by the EWR site. The scenario assessment conducted in the EWR process evaluated the sensitivity of the present ecological condition of the EWR site to proposed developments we are aware of and the worst-case climate change scenario. These assessments were conducted at the EWR reach scale and were not intended to result in recommended classes for the water resources.
76 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Evidence of the commitment by DWS to the MMSEZ Our concerns about the lack of adequate representation in the Reserve determination process and apparent dominance of the Project Steering Committee by the DWS, given the PSC’s influence on the process, are greatly amplified by the DWS’ declared support for the MMSEZ, a China-South Africa state-backed industrial mega-project based on the exploitation of the Limpopo’s coal resource endowment, that will have severe adverse impacts on the water resources of the Limpopo-Olifants WMA and the Limpopo River itself. | Adhishri Singh | Please note that within the DWS, different departments are tasked with various mandates for managing South Africa’s water resources. The fact that the Chief Directorate, Water Ecosystems Management is undertaking the Reserve, classification and the Resource Quality Objectives (RQO) of the water resources in the Limpopo and a portion of the Olifants WMA clearly indicates their commitment to sustainable development. It is important to note that the mandates of the DWS relevant to the study will be addressed through the classification and RQO process, which is the next phase of the project. These competing demands on the resources will be weighed against a set of criteria, and trade-offs where necessary will be undertaken.
77 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | In this context, our confidence in the integrity of the Reserve determination process is undermined to the extent that it is being rendered a top-down process driven by the DWS with only limited participation by water-users from other sectors. We reiterate our request for a full disclosure of the composition of the PSC and for a genuine opportunity to participate in the economic scenario modelling and evaluation component of the process. | Adhishri Singh | The composition of the PSC is on the DWS website. If you feel there is a sector missing, please provide their details so we can update the database. The scenario development and evaluation has just begun and stakeholders will be invited to participate in the process.
78 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Ecological Water Requirement We record that we have a number of queries and would like additional information connected to the 19 EWR sample sites selected across the study area. For example, we would like to query why the only EWR sample site for the Nzhelele (at A80G) was not located at the mouth of the river, below the canal irrigation scheme and the recreational dam located on Riverview Farm which impounds the final irrigation scheme allocation in a recreational dam and impedes downstream flow below the height of the 6m dam wall through the declared nature reserve area to the mouth. We note that we drew this to your attention in a presentation and report submitted to you in November 2022 and wish to query why no remedial action was taken. | Adhishri Singh | The site selection process undertaken in selecting the 14 EWR sites is documented in the Site Selection and Verification Report (September 2022) and was based on DWS accepted procedures (King et al. 2008) . The selection of EWR sites is based on various criteria, which include, amongst others, a geomorphologically representative site, location of existing water resource developments and the availability of existing data. The EWR site on the Nzhelele River is downstream of the irrigation agriculture and correlates with the only River Ecostatus Monitoring Programme (REMP) site on this river. The REMP site, A8NZHE-SCHOT, is currently monitored by the DWS and, as such, provided greater sampled data with which to eco-categorise the EWR site and will allow for continued monitoring of the Resource Quality Objectives that will be set once the resource has been classified. The compliance issues raised with the project team regarding the Riverview Farm, as explained to you, are outside of our mandate. It was suggested to you in February 2023 that a formal enquiry be sent to Ms Thenga (thengav@dws.gov.za) or Ms Mbedzi (mbedzif@dws.gov.za), who will direct the matter to the correct DWS Official at the Limpopo Regional Office.
79 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | We note also that five sites were sampled by the Institute of Water Management (IWMI) as part of another study for LIMCOM. We request additional information on the process to reconcile the results, findings and recommendations of the secondary and mainstem studies | Adhishri Singh | For information on the 5 EWR sites selected and sampled by the IWMI as part of the LIMCOM study, refer to the series of reports titled E-Flows for the Limpopo River Basin. Dr Chris Dickens at the IWMI is the contact person for the Limpopo Watercourse Commission (LIMCOM) study.
80 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Eco-categorisation: present Ecological State and Ecological Sensitivity and Importance Assessments We record that we have a number of queries and would like additional information connected to the sampling sites and data inputs. For example, the aquatic and riparian zone species data collected at the EWR sampling site for the Nzhelele (A80G) does not agree with the data collected and results of the many surveys we have conducted in the lower reaches of the river. We therefore disagree with the EIS rating. | Adhishri Singh | It is important to note that the eco-categorisation process was conducted for the EWR site and not the catchment as a whole, as indicated in your comments. The EWR Report – Rivers (Vol 2) Data Collection and Analysis contains information on the data sampling and data used in the eco-categorisation process.
81 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | We note further in this regard that the Protected Areas Network (PAN) seems incomplete on the map of the study area shown, and that there is no Critical Biodiversity Areas map (CBA Map) overlay or reference to the district bioregional plan, which based on our understanding of the requirements, should have been consulted. We are therefore concerned that the sampling sites selection may not accurately reflect the actual ecological sensitivity and value of the water resources. For example, the Philip Herd Nature Reserve on the mouth of the Nzhelele River (A80G) is not shown, nor is the surrounding, informally protected CBA1-classified area, and the sampling site selected falls outside of the nature reserve and CBA1 area. | Adhishri Singh | The selection of the EWR sites is based on several criteria, as explained for the Nzhelele EWR site above, and they will not necessarily be situated within a nature reserve or Critical Biodiversity Areas (CBA) classified area. CBAs and other areas of conservation importance have not been overlooked and will be consulted in the development of scenarios.
82 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Socio-economic component: Provisional Recommended Ecological Class (RECs) We record that we do not agree with the proposed desired state of most of the water resources, as defined by the recommended classification of each water resource and associated water use. An improvement is recommended in only 4 of the 19 Quaternaries from a PES rating of “C” to “C/B”. We would argue strongly that greater improvements are both desirable and attainable within the nature-based, conservation-led economic development framework for the region for which we advocate, which will yield improved ecosystem function, ecosystem services provision, food and water security and climate change mitigation and adaption and the resilience of the entire river system. Further, as the Reserve study observes, the overall ecological state of a water resource (as reflected in the condition of the ecosystem, geomorphology, riparian vegetation, invertebrates and fish species diversity) correlates with higher recreational and cultural value, overall social well-being, nature tourism value, fisheries value, plant and other natural resource value, wildlife and domestic livestock watering and thus capacity, and carbon retention value. In the context of nature-based economic development, the traditional trade-offs between economic and environmental benefits and costs are vastly reduced. | Adhishri Singh | We would like to reiterate that the classification of water resources has not yet been undertaken. The REC in the technical reports is the Recommended Ecological Category, not the Recommended Ecological Class as mentioned in your comments. This is the recommended ecological condition for the river reach represented by the EWR site, based on the present ecological condition, the Ecological Importance and Sensitivity (EIS) and assessing if the condition could be improved by factors other than flow, such as removal of exotic vegetation and continuing efforts to curb bank erosion.
83 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Scenario modelling and effect on RECs We record our concern that the assessment of the impact of the expansion of coal mining and heavy industry on the scale planned that will guide the Water Resource Class and Reserve determination, understates their real impact on the water resources of the affected catchments, as well as the risks to all water users dependent on the water resources. This includes concerns about the Basic Human Needs Reserve and comments on the progress report WP 11352, December 2023, as already communicated with the consultant and DWS. We disagree in particular with the Future Ecological Status predictions based on the development plans in relation to the Present Ecological State (PES)5 and Recommended Ecological State (REC) for each water resource (“Future 1”). We are of the opinion that the methodology employed is flawed for the reasons set out below: | Adhishri Singh | Please note that the expansion of coal mining and heavy industries will not guide the classification but will be an input to the classification process. The implications of those expansions will be determined accordingly in the various scenarios to be developed. The comments on the Basic Human Needs Reserve have been received and addressed as indicated in the Comment and Response Register (above)
84 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Grossly understated impacts of coal mining and the MMSEZ Development scenarios and predicted outcomes on Overall Ecological State: We note that the socio-economic component of the Water Resource Classification System process being followed involves economic development scenario modelling, which will inform the Water Resource Quality Objectives set and final recommended Class of each water resource (which will guide all future water resource management decisions). A development scenario has been modelled for each catchment, which concentrates on the planned expansion of coal mining, the development of the MMSEZ industrial zones and urbanisation. The scenarios are purportedly the “worst case” impact scenarios based on meeting the water needs of developing these extremely water-intensive sectors. The predicted impact of these development scenarios on the overall state of the water resources under normal “Future 1” and drier climate “Future 2” conditions is assessed in relation to the Present Ecological State (PES) and Recommended Ecological State (REC) for each water resource. The outcome of the base case scenario on the flow regime for the catchments and their ecological condition ranges from degradation to Class D for the Nzhelele and Nwanedi, to maintenance of the PES for the majority of catchments to – incredulously – an improvement (to Class B/C) for the Sand River (under Future 1 conditions) despite the fact that it is over-exploited, will host the MMSEZ smelter and coal mining, and that a mega-dam complex will be constructed at the river mouth. | Adhishri Singh | The effect of the Future Scenario flow regime on the ecological condition, social use and economic value was considered for the river reaches represented by the EWR sites. The Sand River EWR site showed an improvement under Future 1 flow conditions because increased return flows and incoming inter-basin transfers improved the flow conditions at the site, which improved the ecological condition. The proposed developments in the lower Sand River did not impact the EWR site, which is situated upstream of these developments.
85 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Water demands and supply plans for the MMSEZ and coal mines The assessed water requirements of the planned MMSEZ Energy-Metallurgical Zone (EMSEZ) at the South Site and subordinate North Site, together with the new coal mines to be developed in the Greater Soutpansberg Coalfield to inter alia supply the industrial zones, are in the order of 115Mn3/a and dwarf the available water resources of the already-stressed Nzhelele and Sand River catchments in which they will be located. | Toriso Tlou | We have taken note of the water demands for the MMSEZ, but please note that as far as we are aware, only site 2 of the MMSEZ, which is Musina site 2 has been gazetted and Makhado site 1 has not as yet. Therefore, we will address these separately in our development scenarios. Also note that in the development of MMSEZ, various water resource development options, ranging from transfers from Beitbridge (please note that Zhove Dam is no longer considered as an option) to dam developments in neighbouring catchments and transfers from existing systems will be considered to meet the demands referred to and these will be factored into the classification process.
86 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Masking real impacts and risks of the MMSEZ and coal mining The fairly negligible or even positive predicted impact and risk of large-scale mining and industrial development on the water resources according to the EWR report is a result of the conservative RECs – little improvement is recommended – and because under the methodology employed: - assessments are conducted for discrete catchments – the Integrated Units of Analysis IUA-scale assessments are not in fact integrated at all, and - only abated impacts are considered i.e. impact is evaluated after factoring in planned infrastructure development to enable inward transfer schemes to supplement available water resources. In other words, the base case scenario modelled is far from the worst case. The worst case baseline is quite patently the deficit exposure of the water demands of the SEZ and coal mines in the absence of any infrastructure development to “augment” inadequate available water sources with water from other catchments that purportedly have a surplus via “inter-basin” or “inward transfer” schemes). We note in this regard that while a full deficit exposure appears nowhere in the Reserve study reports, nor other Integrated Water Resource Planning instruments, including the Limpopo WMA Reconciliation Strategy or in the EIA for the MMSEZ, according to the projected water balance that is disclosed in the Internal Master Plan13 for the EMSEZ (see extract below), the deficit that will emerge after factoring in water demands of the MMSEZ [EMSEZ], the new mines servicing the SEZ and the projected domestic needs of the two municipalities, Musina and Makhado LM, is estimated to be -167.65 Mn3/a. This apparently excludes the water demands of the North Site of 20Mn3/a. To meet “Phase 3 demand” according to the Master Plan extract, the estimated “transfer capacity” needs to be 133 Mn3/a. This is an extremely serious exposure, in particular for domestic water users, and in particular in the Musina LM, whose water needs are currently in the region of 6-8 Mn3/a rising to 11-24 Mn3/a by 2040 with very poor assurance of supply. It seems a gross lapse not to include such an unabated impact assessment as the baseline scenario in the socio-economic assessment for the Reserve determination. | Adhishri Singh | Please note that integrating the Integrated Units of Analysis (IUAs) is done based on the hydrology of the whole system and not per IUA. In that context, the assessments used to determine the flow-based ecological categories are integrated at the hydrological level of the system. This includes natural flows, transfers and return flows. In the development of MMSEZ, various water resource development options will be considered to meet the demands referred to and these will be factored into the classification process.
87 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | As it is, the Reserve study does not consider the impact in relation to the PES (Present Ecological State) or REC (Recommended Ecological Class) of the partial or complete failure to develop such transfer capacity in its “worst case” scenario. Instead, the water demands are effectively ‘transferred’ to the Limpopo mainstem or other catchments beyond the scope of each secondary catchment assessment by – irresponsibly – assuming that the surpluses are available and the enabling infrastructure is developed to transfer the water, which distorts and minimises real impacts and risks. The otherwise-sound principles of catchment-level water resource management and water balancing is effectively being used to avoid assessing the cumulative impact of these plans within a properly integrated framework for the Limpopo WMA and Limpopo River. The dangerous result of basing the risk assessment on the unfeasible inter- and intra-basin transfer schemes, and ignoring the transferred impacts for the Limpopo River and other catchments, is that the water impacts of the exploitation of the Greater Soutpansberg Coalfield and the development of the carbon- and water-intensive industrial zones of the MMSEZ on already-stressed catchments in a water-scarce region are presented as having been assessed and deemed benign or even positive, which will support their authorisation. According to the modelling, the planned expansion of coal mining and heavy industry could proceed at a cost of ‘just’ one catchment – the Nzhelele/Nwanedi. The recommendations for future ecological classes made unilaterally, mostly to merely maintain the status quo, can be achieved in all but the Nzhelele/Nwanedi catchment, which will be degraded to Class D. | Adhishri Singh | Please note that integrating the Integrated Units of Analysis (IUAs) is done based on the hydrology of the whole system and not per IUA. In that context, the assessments used to determine the flow-based ecological categories are integrated at the hydrological level of the system. This includes natural flows, transfers and return flows. In the development of MMSEZ, various water resource development options will be considered to meet the demands referred to and these will be factored into the classification process.
88 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Degradation of the Nzhelele-Nwanedi to Class D First, our concerns about the minimisation of impacts notwithstanding, we note the predicted degradation of the Nzhelele and Nwandei catchments to Class D (from a present and recommended Class C) as a result of the impact of the development of coal mining and MMSEZ (Future 1), and to Class D/E under a drier future climate scenario (“Future 2”). We record our objection to this outcome for these water resources, their water users and nature reserves located in this quaternary, for the benefit largely of coal mining and foreign interests. | Gerald Howard / Dr Karl Reinecke | The future development in the Nzhelele catchment consisted of: 1) Increasing the demand on Nzhelele Dam from 2.2 Mm3/year to 4.8 Mm3/year. This demand supplies the Nzhelele Domestic Water Supply. 2) Increasing the demand on Mutshedzi Dam from 4.3 Mm3/year to 7.3 Mm3/year. 3) Adding the proposed Mutamba Dam to supply Makhado Coal Mine with 1.92 Mm3/year It is noted that local water users in the Nzhelele catchment will also benefit from an additional 5.6 Mm3/year compared to 1.9 Mm3/year for the Makhado Coal Mine. It is important to note that all the EWRs are preliminary. The decision on which flows and conditions are chosen takes place during the analysis of scenarios during the Classification process, that we are starting now. Your rejection of the predicted reduction in ecological condition is noted. There are going to be more scenario analyses taking place now during the Classification process that will consider flows basin wide and not just at the EWR sites. There will be more than the four scenarios that were analysed during the EWR study for consideration. The classification process and associated scenario analysis will aim to find the appropriate balance between the level of environmental protection possible and the use of the water to sustain socio-economic activities. There is opportunity to provide inputs into the construction of these scenarios and in particular towards selecting the scenario that goes forward and gets signed off for each river. That will contain the final decision on the flows and the ecological condition associated with it.
89 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Second, we note that under a drier future climate scenario (“Future 2”), the predicted outcome for overall ecological condition and the flow regime is far worse across the catchments, and particularly for catchments such as Mutale that will also be degraded to Class D. We have a number of queries and request additional information to understand the parameters of this drier climate model and whether this scenario will be used as the default under the precautionary principle, and if not, why not. This is of particular concern to us since allowance is made for ECs to be below RECs within the adopted Reserve and WRC framework. For example in the July 2022 PSC1 BID it is stated in the section on Linking the Value and Condition of the Water Resource (Table 2: Preliminary Scenarios) that: High ECs are given to areas of high conservation importance, but for other areas, the ECs can be below REC. It may end up that this scenario set is similar to the above. | Gerald Howard / Dr Karl Reinecke | Climate change data is available on the World Bank Climate Change Knowledge Portal (CCKP). Details regarding the development of climate change models can be located using the following link: (https://climateknowledgeportal.worldbank.org/) Six global climate change models are strongly recommended for use in South Africa of which the Australian Community Climate and Earth System Simulator (Access-cm2) was selected for use. This is one of the most severe with regards to reduction in runoff. Other models indicate less severe reductions in runoff, and one of the six models shows very little change. The severe Access-cm2 model has been included only to indicate a “worst-case scenario”. The Future2 scenario was constructed by overlaying the severe drying climate onto Future1, both of which were considered to be worst case scenarios because Future1 gathers all the projected water use for all the known proposed developments. We therefore don’t believe it is the best scenario to use as the default under the precautionary principle. There are going to be more scenario analyses taking place during the Classification process that will consider flows basin wide and not just at the EWR sites.
90 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Synthetic scenarios Third, for those catchments that will suffer significant deterioration in quality and quantity of water flow even under Future 1 climate conditions, we note that a “Synthetic Scenario” (SS) has been modelled to “allow for development and predict a better Ecological Status than Future 1”. According to the PSC2 Information document: In cases where the predicted Ecological Status under Future1 is poorer than PES, Synthetic Scenarios (SS) were created that allow for development and predict a better Ecological Status than Future1. The Synthetic Scenarios explored scenarios by increasing baseflow in the dry season (mostly) to test whether the predicted Ecological Status could be improved. The increases were unrelated to the planned developments. We have a number of queries and request additional information in connection with the SS. The information provided is insufficient to understand and assess the viability of this option. We do not understand what practical measures are proposed to manipulate baseflows, particularly in the dry season. How would additional flow be released into these water resources and from where would it be sourced? Would the improvement be limited to the flow volumes but not water quality? Finally we expressly record that we dispute the predicted improvement in the Sand River catchment to a Class B/C for the reasons cited above. | Dr Karl Reinecke | The modelling of a SS was done to explore the theoretical possibilities of maintaining a better ecological status than that predicted by Future1 by reducing the demand for low flows in the Future1 scenario. The viability or implementation was not considered. The improvement in low flows, by reducing the demand of Future1, was modelled in the DRIFT software and the overall ecological condition for the EWR sites is a result of the combined responses of water quality, geomorphology, riparian vegetation, aquatic invertebrates and fish to hydrological and hydraulic changes. The purpose of this scenario was to illustrate that if development were to take place as planned then consideration could be given to curtailing demand for low flows to reduce the effect on river condition.
91 | 2024-04-22 | Dr Victor Munnik | Living Limpopo, the Sand-Nzhelele-Luvuvhu Water Resources Research Forum and the International Water Management Institute | Comment on the EWR and BHNR reports (PSC2) | Conclusion and request for participation As set out herein, we are concerned both with respect to the basic decision on whether to manage our water resources ‘up’ or ‘down’ (the environmental trade-off to support economic – mining, industrial or agricultural – development) and our right as water users and stakeholders to participate in those decisions. We welcome the assurances that we still have an opportunity as stakeholders to propose alternative, more sustainable, equitable, less water-intensive nature-based economic models that will foster climate change resilience – and that will support actual improvement in the ecological state of the water resources instead of their degradation, and that these alternative scenarios will inform the final recommendation and determinations on the Water Classes (which amounts to the decision on how the water resource will be used and managed and their future ecological condition. We look forward to your considered response for our request for an extension to the window for comment on the technical reports published and to convene a meeting of stakeholders focussed on the socio-economic scenario development and evaluation. | Adhishri Singh | Stakeholders will have an opportunity to participate in the scenario analysis during 2024. For now, we will use your input to visioning and prepare preliminary scenarios.
128 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 5. More fundamentally, we are concerned that the report fails to show the assessed impact of this abstraction scenario sufficiently clearly for stakeholders, particularly non-technical stakeholders, to understand ‘what will happen to the water resources if we allow maximum extraction for water-intensive economic development with the only proviso that the rivers are not allowed to degrade lower than a Class D where that is possible’, to put the object of this exercise in plainer language. Rather, the report to some degree masks the real impact of this scenario i.e. the extent of the degradation in relation to the already-stressed Present Day situation in our water-scarce region viz-a-viz the serious decline in flow volumes and overall Ecological Condition of the rivers. | Dr Karl Reinecke | We understand the concern and appreciate the suggestions to report summarised results more plainly in tables and figures and have made use of some of the suggestions provided in Section 5. That being said, the intention of this report was never to report fully on the expected outcomes of the ESBC flow scenario because this has not yet been explored and as explained above, the tool remains in DRAFT until all the scenarios have been calibrated. The team are now starting to work on the outcomes of all the scenarios where the outcomes will be more fully expressed. The suggestions on results reporting are noted and will help better present outcomes of all the scenarios in the next report; Scenarios evaluation and draft water resource classes report.
129 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 6. We note in this regard that the ESBC ‘bottom-line’ report is the first in a series that will compare outcomes for the water resources under different scenarios ranging from a. a maximum conservation ‘best attainable state’ scenario (which we would argue is not a ‘low development scenario’ but rather a conservation-led, nature-based sustainable economic development scenario) to b. a ‘[water-intensive industry] development-focussed’ maximum-abstraction-without-any-constraints-on-the-degradation of the water resources ‘No EC’ scenario. Water users and other stakeholders wishing to participate in this Reserve determination process must be able to easily compare the outcomes on the rivers of these different possible scenarios in terms of changes to 1) actual flow volumes and 2) resultant overall Ecological Condition from simple maps, graphs and other graphics representations accompanied by concise, plain-language explanations. The ESBC report in its present form does not meet this requirement. | Dr Karl Reinecke | The ESBC report was intended to explain how the tool (model) that will be used to construct the scenarios was made, what the input data are, and what some output data could be. It is a report on the use of models and considers the hypothetical ESBC flow scenario as an example of what possibe results could look like. The objective is to set up the tool and show that it works. This report was never intended to fully express the outcomes of the ESBC flow scenario, especially because it is likely to change and be revised as the other scenarios are loaded, calibrated and reported. The MAR volumes for Current and ESBC are now in the tables of Section 4, and summarised changes in volume in Section 5 following your suggestions. We anticipate added monthly volumes in an Appendix. We expect that there will be additional requests from our team and stakeholders to provide other kinds of summarised results as we look at the outcomes of the other scenarios.
130 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 7. Together, the apparent errors and resultant misrepresentation of the ecological degradation under this abstraction scenario, inadequate reporting of the most fundamental impact of the scenario – the decline water flow volumes, and the highly technical content which renders the report incomprehensible to most stakeholders, are at odds with the purpose and intent of the scenario evaluation reports and undermine the principles of access to information and informed consent enshrined in PAIA[i] and PAJA[ii] and NEMA[iii] and of participatory decision-making, decentralised water resource management and democratised water governance enshrined in the National Water Act[iv]. | Dr Karl Reinecke | As already explained, this is a report about hydrological modelling, and not a report that was supposed to report the outcome of the ESBC flow scenario fully. The main response for this are that the outcome has not yet been analysed by the team (water quality, wetlands, groundwater, socio-economics), and the outcome of the ESBC flow scenario is a work in progress at this point. The suggestions to better express changes in flow are understood and will included in the Scenarios evaluation and draft water resource classes report.
131 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 8. As we have repeatedly argued in previous submissions, it is unacceptable that the Reserve determination and attendant far-reaching decisions about our water resources and their management are being taken in the absence of a functioning Catchment Management Agency (CMA) and indeed, whilst the Limpopo-Olifants CMA (LOCMA) is being established, and with grossly inadequate stakeholder representation on the Project Steering Committee (PSC) presiding over this Water Resource Class, Quality Objectives and Reserve setting process. In this context, it is essential that the study reports published genuinely serve their purpose of showing the assessed impacts of alternative water use and water resource management decision scenarios on the water resources, and that they do not serve to further compromise the rights of water users and stakeholders in the affected catchments. We urge the PSC to consider our recommendations on the presentation of results and findings of this scenario in this report and the other scenarios yet to be modelled. | A Singh, Dr Karl Reinecke | As responded previously, in the absence of a functioning Catchment Management Agency (CMA), the DWS Regional Office assumes the role of the proto-CMA. Despite this, the classification process will strive to consult widely and ensure a reasonable public participation process. Conducting a Reserve is not subject to the establishment of a CMA. The sectors represented on the PSC include Government (National, Provincial and Local); Agriculture, Mining, Industry, Power, Catchment Management Forums, Water User Associations, Water Boards, Transport, Education, Research, Conservation and Environmental bodies, Traditional Leaders. All sectors are invited to Project Steering Committee (PSC) meetings. Should you feel there is a sector missing, please provide their details so we can update the database. As stated above, the Scenarios evaluation and draft water resource classes report is where the outcomes of alternative water use and management decisions will be more fully expressed. We appreciate the recommendations on the presentation of results and have included all the suggestions made for this report...and will take them over into the next report. We would like to reiterate that the results reported on in this report are DRAFT and may change as the work progresses and adjustments are made in the tool as the other scenarios are calibrated.
139 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 17. The correct maps shown in Section 1 Executive summary as Figure E1 and Figure E2 and again in Section 5 Conclusion as Figure 5.1 and Figure 5.2, whilst helpful as a visual representation of the outcome of the ESBC 'bottom line' scenario aross the river reaches, still only show the change in Ecological Condition from the present day situation | Dr Karl Reinecke | No comment required.
140 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 18. The impact of semi-constrained maximum abstraction on actual flow volumes is not shown in a map or chart, nor is the data summarised in the Executive Summary or elsewhere, which we consider a serious oversight: | Dr Karl Reinecke | Results that summarise the flow volumes are now included in Section 5.
141 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 19. This study aims to determine what impact maximum abstraction will have on the water resources with certain ‘soft limits’ on the allowed ecological degradation. Accordingly, it is patently necessary to show in the first instance, the impact of maximum abstraction on the volume of water in the river systems – both on Present Day flow volumes and compared to Natural State flow volumes, since Mean Annual Runoff (MAR) is already well below natural water volumes for most catchments, as the report clearly shows. Although flow volumes are an important determinant of the Ecological State of a water resource, as the ESBC report notes at Section 4 Results of the ESBC Scenario, other factors can impinge on the Ecological Condition, while by contrast, the Ecological Condition measure can mask a serious decline in flow volumes, such as when reduced flows also diminish seasonal variation (although we are of the view that the negative impacts of reduced flow tend to vastly outweigh any flow regulation benefits). | Dr Karl Reinecke | Results that summarise changes in flow relative to present day and natural are now included in Section 5.
142 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 20. The Present Flow States categorised as A-F (with corresponding colour codes) for each node and river reach are shown in Section 3 The Balancing Tool in Table 3.3. However, the equivalent predicted Flow State categorisation under the ESBC scenario is not shown anywhere. | Dr Karl Reinecke | The MARs of Natural, Current and ESBC are now included in the tables of Section 4.
143 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 21. The total actual annual flows as percentages of natural and surpluses or deficits relative to current day flow are however, shown in section 4. Results of the ESBC Scenario and in section 5. Conclusion Table 5.2 Summary results for the ESBC scenario for all nodes, showing the Ecological State, annual percentages of natural and season deficits/surpluses (Mm3). We have summarised these flow results reported in Table 5.2 and presented them graphically below. | Dr Karl Reinecke | Thank you, we have included the graph into the results and included a paragraph that talks to the new figure.
144 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 22. According to the results contained in Table 5.2, under the ESBC scenario, flow volumes decline in every catchment in the study area by between 17% and 55% from present levels. Aggregated across all 75 nodes, 604Mm3/a is lost (17% of the water) – from 3,583 to 2,814Mm3/a. | Dr Karl Reinecke | As above.
145 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 23. Current flow volumes range between 62% and 96% (Shingwedzi) compared to natural flow volumes, with a median score of 73%. Under the ESBC abstraction scenario, flow volumes decline to between 43% (Shingwedzi) and 62% i.e. the Present Day lowest level and worst catchment would be the highest and best in the ESBC scenario. The medium flow volume under ESBC abstraction rates declines to a mere 55% of natural, far below the Present Day flow volumes. | Dr Karl Reinecke | As above.
146 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 24. It bears repeating in this context that the Limpopo-Olifants WMA is an arid climate, water-scarce region whose catchments are already severely stressed. Natural flow volumes are comparatively low and have already declined significantly. A precipitous further decline in flow volumes from present levels is a serious threat to the resilience of the entire Limpopo River Basin and all water users dependent on its water resources. | Dr Karl Reinecke | We agree with you and have included a statement to that effect in the conclusion of Section 5. As mentioned earlier, the ESBC flow scenario is in our opinion purely hypothetical and is not likely to be selected by stakeholders. However, the outcomes expected for all the scenarios will be presented in the same manner and more fully expressed in the scenarios evaluation and draft water resource classes report, next in the series and will remain in DRAFT until agreement is made on which scenario will be taken forward. The results will then be finalised and submitted in the FINAL scenarios report.
147 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 25. The serious adverse impact on already-reduced flow volumes (compared to fairly limited natural flow volumes in our arid region) of allowing the maximum abstraction for economic activities even subject to weak ecological constraints (of maintaining the rivers ‘where possible’ at no worse than a ‘D’ state) warrants emphasising in the results and conclusions of the ESBC Report. Neither the Executive Summary nor the Conclusion makes any reference to flow volumes. We consider this a serious flaw. | Dr Karl Reinecke | Thank you and as above. Flow volume summaries are now included in both the Executive Summary and the Conclusion, along with statements giving context about aridity and water scarcity, as suggested.
148 | 2024-07-22 | Barbara Van Koppen | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | 26. For most water users, the actual amount of water in the river system is the single most important factor – it’s in fact, the ‘bottom line’. Water users and other stakeholders are entitled to know – and to be shown clearly and ‘up-front’ (in the Executive Summary) with maps showing the Natural and Present Flow State compared to ESBC Flow State (equivalent to the Ecological Condition comparison maps) and graphs as shown above – what is the basic and immediate impact of allowing the maximum amount of water to be extracted for economic development of water-intensive industries such as mining, including coal mining, heavy industry and manufacturing and irrigation agriculture/industrial agriculture: a decrease in the volume of water in the river systems. | Dr Karl Reinecke | This is an interesting suggestion and we have included maps and graphs that show natural and present flow state relative to ESBC flow state.
149 | 2024-09-16 | Lauren Liebenberg | Sand-Nzhelele-Luvuvhu Water Resources Research Forum | ESBC report comments | Regarding the Nzhelele's Ecological Water Requirement Assessments to date in the preliminary reports, it was highlighted that if no effort is made in the latter reports to address the issue that she has raised since 2022 around the sampling sites on the Nzhelele upstream of the recreational dam that impounds an irrigation allocation from the Nzhelele dam and therefore starves the lower reaches of any water flow for prolonged periods of time. The report states repeatedly that there is more than suffiecient water in the system to make provision for the ecological component of the reserve including on the Nzhelele, there are zero flow days at present being experienced, the onset of dry season and wet season are close to historical and this is absolutely false. They have been monitoring the zero/no flow conditions that persist there for protacted periods inflicting immense damage on the river ecosystem and the riparian zone habitats. There is zero recharge into the limpopo mainstem and they have been undertaking the monitoring over the last 20 years, since the construction of the dam. This is a critical biodiversity area and protected areas, through which the river flows and the ecologicial sensitivity and importance in those lower reaches are far higher than the middle reaches of the river. The overall downgrading of the system to a class C, reflects the facts that it is heavily modified from natural with the irrigation system, dam and scheme supplied by the dams yield. They are down there in the lower reaches, with zero flow for the last 20 years, for most of the year for a river that is still classified as perenial is seasonal, marginally at this point and this is not acknowledged. Once the CMA is established and is up and functioning, they will have no remedy as their disposal to insist upon the interventions to make express allocation for the reserve in the releases from the dam to the mouth of the river, with a monitoring site at the mouth of the river in the future. She explained, that this will then leave her arguing to fix a problem that does not exist according to the report. However, this problem does exist and the reports contradict the evidence on the ground and is inconsisten with what was conceded in the North Limpopo WMA Reconciliation Strategy balancing equations and LIMCOM Assessments. In the Reconciliation Strategy, there is an acknowledgement that the Nzehelele catchment is overallocated in the absence of provision for the reserve. In the LIMCOM E-Flow studies, there's a flow reduction throughout the basin, that can be observed and this is not being identified in the case of the Nzhelele because the sampling site distorts the results as it is measuring an irrigation allocation that is then impounded in a recreational dam unlawfully. The flow reduction stresses that are being experienced in the lower reaches of the Nzhelele due to the failure to make provision for the ecological component of the reserve for the ecological flow requirement in the releases form the Nzhelele dam. She also suggested including recommendations that go so far as to say the Ecological Flow Requirement in the releases from the Nzhelele dam will reach the mouth from the irrigation system, including the impoundments in the lower reaches.